## Sheet1
Synapse — Integration QC Test Plan (BizTalk-Style)
# | Module | Test Case | Expected Result | Priority | Status | Notes
Schema Validation
1 | Schema Validation | Valid input record passes schema validation and proceeds to transform stage | Record passes; transform executes; no validation error logged; run_manifest shows 'validation: pass' | High | Blocked | No validation stage / run_manifest in Synapse (transform-only pipeline)
2 | Schema Validation | Record with missing mandatory field rejected at validation stage | Record quarantined; error log contains: field_name, record_id, error='mandatory field null'; downstream stages not triggered | High | Failed | No per-record quarantine of missing mandatory fields
3 | Schema Validation | Record with wrong data type (text in numeric field) rejected | Record quarantined; error log: field_name, received_value, expected_type='numeric'; count incremented in run manifest | High | Failed | No type-based record rejection (values coerced or passed through)
4 | Schema Validation | Record with field value exceeding max length constraint rejected | Record quarantined; error log: field_name, value_length, max_length; not silently truncated | High | Failed | No max-length constraint concept in mapping/validation
5 | Schema Validation | Batch with mixed valid/invalid records: valid records processed; invalids quarantined | Valid records continue to transform; invalid records in dead-letter queue; counts reconcile: valid+invalid = total | High | Failed | No valid/invalid split or dead-letter of bad input records
6 | Schema Validation | Schema version mismatch detected (source changed structure without notice) | Connector pauses; alert raised to Arch Lead within 5 min; last-good schema version logged; no partial load | High | Failed | No runtime schema-drift detection or auto-pause
Data Transformation
7 | Data Transformation | Lookup/code transform: source 'emp_status' = 'A' maps to target 'Active' | All configured code mappings produce correct target values; unmapped codes default to 'Unknown' and are flagged | High | Blocked | codeMap preset + Wizard/Canvas config UI shipped & verified 16-Jul ('A'->'Active'; unmapped->'Unknown' fallback). Gap: unmapped codes are NOT flagged/logged.
8 | Data Transformation | Date format normalisation: source dd/MM/yyyy → target YYYY-MM-DD (ISO 8601) | All date fields converted correctly; invalid dates (e.g. 30-Feb) rejected with error log | High | Blocked | parseDate preset + format picker shipped & verified 16-Jul: dd/MM/yyyy->ISO correct; 30/02 rejected as null (no silent rollover). Gap: invalid dates written as null, not error-logged.
9 | Data Transformation | Currency normalisation: USD and GBP amounts converted to INR at configured exchange rate | Rate applied = rate configured for run date; converted values within 0.01% of manual calculation | High | Blocked | currency preset (rate + decimals) shipped & verified 16-Jul: 100 x 83.2 = 8320 exact; non-numeric->null. Gap: one static rate per mapping; no rate-by-run-date table.
10 | Data Transformation | Derived/calculated field: attrition_rate = (leavers / headcount_start) × 100 | Calculation correct to 2 decimal places; division-by-zero handled gracefully (result = null, flagged) | High | Blocked | divide preset shipped & verified 16-Jul: (leavers/headcount) x 100, 2dp, div-by-zero -> null (never NaN/Infinity). Gap: null result is NOT flagged.
11 | Data Transformation | Conditional transform: project_status = 'green' AND utilisation < 70 → flag 'underutilised' | All qualifying records flagged; non-qualifying records have null/empty flag field; edge cases (exactly 70) correctly handled | High | Pass | Arbitrary conditional logic runs in quickjs expression sandbox
12 | Data Transformation | Null/empty source field uses configured default value — not written as null to Pulse DB | Default value per field defined in transform config; applied correctly; original null logged in run manifest | High | Blocked | default preset + config UI shipped & verified 16-Jul: per-field configured value substituted when source is null/empty. Gap: original null not logged (no run manifest).
13 | Data Transformation | String concatenation: first_name + ' ' + last_name → full_name | No extra spaces; names with special characters (apostrophes, accents) handled correctly | Medium | Pass | concat preset space-joins fields; handles special chars
Adapter — HR
14 | Adapter — HR | HRMS: connect via JDBC; full employee extract matches source record count | Extracted count = source system employee count for same filter; connection closed cleanly after extract | High | Blocked | HR = generic DB connector instance; connects+extracts, count-match needs live system
Adapter — Finance
15 | Adapter — Finance | Finance ERP: connect via REST API; all P&L line items for period extracted | API response paginated correctly; all pages fetched; line item count matches ERP report | High | Blocked | Finance = generic REST connector; full extract needs live ERP
Adapter — Delivery
16 | Adapter — Delivery | PM tool: connect via REST API; all active projects and tasks extracted | All projects with status ≠ 'archived' extracted; task count per project matches PM tool | High | Pass | Jira is a real REST adapter (projects+issues) - delivery/PM source
Adapter — Accounts
17 | Adapter — Accounts | Accounts system: connect via database view; full AR ledger extracted | All open AR entries extracted; closed entries excluded per filter; count matches Accounts team export | High | Blocked | Accounts = generic DB connector reading tables/views
Adapter — Sales
18 | Adapter — Sales | CRM: connect via REST API; all opportunities in configured stages extracted | Stage filter applied correctly; custom fields mapped; API rate limit handled with back-off | High | Blocked | Sales = generic REST connector; pagination available
Adapter — Inside Sales
19 | Adapter — Inside Sales | Dialler system: connect via REST API or SFTP file drop; call log for period extracted | All calls within configured date range extracted; call disposition codes mapped to Pulse schema | High | Blocked | Inside Sales = generic REST + SFTP file listing (no content parse)
Adapter — Marketing
20 | Adapter — Marketing | MA platform: connect via REST API; campaign, lead, and email metric data extracted | Campaign list, lead list, and engagement metrics all extracted; attribution data included | High | Blocked | Marketing = generic REST connector
Adapter — Admin
21 | Adapter — Admin | ITSM/FM system: connect via REST API; ticket and asset data extracted | Open and closed tickets for period extracted; asset register snapshot extracted | High | Blocked | Admin = generic REST (tickets yes, asset register not modeled)
Adapter — Connectivity
22 | Adapter — Connectivity | Source system returns 401 Unauthorised (credential expired) | Connector fails gracefully; alert sent with source system name and error; no partial data written; secret rotation triggered | High | Blocked | Fails gracefully on 401; run-failure alert now raised into app.alerts by alertDispatcherWorker (15-Jul). Gap: alert not delivered (no mailer), not 401/source-specific; no auto secret-rotation.
23 | Adapter — Connectivity | Source system unavailable (connection timeout after 30s) | Connector retries 3× with exponential back-off (30s, 60s, 120s); marks run as failed after 3rd retry; alert raised | High | Blocked | Backoff ~1-8s not 30/60/120s; no 30s timeout; RedGold retries 429 only
Message Routing
24 | Message Routing | HR records routed to HR_staging table; Finance records to Finance_staging only | No cross-routing; record counts per staging table match source extract counts; no HR record in Finance_staging | High | Blocked | Per-source topic isolation (no cross-delivery); not dept-staging routing
25 | Message Routing | Content-based routing: records with dept_code = 'FIN' enter Finance pipeline exclusively | All FIN-coded records in Finance pipeline; non-FIN records absent from Finance pipeline; no records lost | High | Failed | No content/payload-based routing (topic-based only)
26 | Message Routing | Unknown/unmapped dept_code: record sent to dead-letter queue with routing error | Record appears in DLQ with error='no route defined for dept_code X'; not silently dropped; alert raised | High | Failed | Unmapped record settled skipped, not dead-lettered + no alert
27 | Message Routing | Routing rule update: new dept_code added; new records follow new route; existing records unaffected | Config update without connector restart; next run applies new routing; historical records unchanged | Medium | Blocked | Subscriptions refresh live without restart; topic-based rules
Orchestration
28 | Orchestration | End-to-end pipeline: Extract → Validate → Transform → Load to Pulse DB in sequence | All stages complete in order; run_manifest shows start/end timestamp per stage; no stage skipped | High | Blocked | Pipeline runs stages sequentially; no per-stage run_manifest timestamps
29 | Orchestration | Dependent stage failure halts downstream stages; upstream completed stages not re-run | If Transform fails, Load does not execute; Extract result preserved; run status = 'failed at transform' | High | Blocked | Throw halts remaining steps; idempotency skips delivered; no resume ledger
30 | Orchestration | Parallel connector runs (HR + Finance simultaneously): no data collision in Pulse DB | Each connector writes to isolated staging table; no row in Pulse DB overwritten by wrong connector | High | Pass | Each target isolated (own table + per-dest idempotency); workers concurrent
31 | Orchestration | Long-running extract (>10 min): job does not time out; heartbeat logged every 60s | Heartbeat log entries visible in run manifest; no timeout error raised during active extract | Medium | Failed | No heartbeat; watchdog force-fails runs publishing over 10 min (opposite behavior)
32 | Orchestration | Re-run of already-completed batch: system detects prior run and applies incremental logic | Duplicate full-load prevented; incremental run processes only changed records; duplicate-run log entry created | High | Pass | Delta re-sync via watermark + cache; no duplicate full-load
Error Handling
33 | Error Handling | Single failed record written to dead-letter queue with full error context | DLQ entry contains: connector_name, run_id, record_id, error_code, error_message, original_payload | High | Blocked | DLQ stores payload/topic/correlationId/error; no run_id or error_code
34 | Error Handling | Dead-letter queue items visible and reprocessable in admin UI | DLQ items filterable by connector, date, error type; 'Reprocess' button triggers re-attempt; result logged | High | Blocked | DLQ list + Replay/Replay-all wired; filter controls added 15-Jul (status / topic / destination). Gap: no date filter; 'connector' and 'error type' only approximated by topic/dest.
35 | Error Handling | Connector failure mid-run: partial load rolled back; Pulse DB remains in last-good state | Pulse DB row count identical before and after failed run; no partial inserts; transaction rollback confirmed | High | Failed | No run-level transaction; per-record commit - no rollback to last-good
36 | Error Handling | Source system returns HTTP 500 error: Synapse does not write any data to Pulse DB | Run marked failed immediately on 500; no records written; run_manifest records error response body | High | Pass | Source error precedes publish -> nothing written, run marked failed
37 | Error Handling | DLQ depth alert: if DLQ > 100 items, alert sent to Infra Lead within 5 minutes | Alert delivered (email/Slack/Teams) within 5 min of threshold breach; alert contains DLQ depth and connector name | High | Blocked | alertDispatcherWorker raises a DLQ-depth alert into app.alerts, threshold from config (verified live: 372 failed vs threshold 100). Gap: no email/Slack/Teams delivery (backend has no mailer); alert is DLQ-wide so carries depth but no connector name.
38 | Error Handling | Poisoned message: record causes repeated failures → quarantined after 3 retries | Record retried 3× with back-off; on 3rd failure, moved to poison queue; does not block processing of subsequent records | High | Pass | Dead-letters/poisons after retries; per-message so others unaffected
Retry & Idempotency
39 | Retry & Idempotency | Transient source timeout: Synapse retries 3× with exponential back-off (30s, 60s, 120s) | Retry intervals match config; each retry logged with attempt number; success on retry = run completes normally | High | Blocked | Exponential backoff + logged retries, but ~1-8s not 30/60/120s
40 | Retry & Idempotency | Duplicate batch submission (same batch_id): second run detected and skipped | Idempotency key (batch_id) checked before processing; duplicate logged; no data re-written; admin notified | High | Blocked | Per-record idempotency (naturalKey:checksum); no batch_id-level key
41 | Retry & Idempotency | Re-delivery of same record: upsert logic updates existing row; no duplicate in Pulse DB | Upsert key (e.g. employee_id) used; existing row updated; row count unchanged; updated_at timestamp refreshed | High | Blocked | Upsert updates existing row (no dup) but updated_at not auto-refreshed
42 | Retry & Idempotency | Manual retry of failed job: resumes from failed step only; completed steps not re-run | Extract (if completed) not re-run; Transform/Load retry from failure point; no data duplication | High | Blocked | Manual replay of failed dest; skips delivered; no intra-job step resume
Transaction Integrity
43 | Transaction Integrity | Batch load is atomic: if last record fails, entire batch rolled back | Pulse DB shows zero records from failed batch; no partial inserts; atomicity confirmed via row count check | High | Failed | Batch loader per-row auto-commit; no atomic batch transaction
44 | Transaction Integrity | Database constraint violation (FK or unique key): transaction rolled back; error logged | Violation error logged with: constraint name, offending value, connector name; no partial data in Pulse DB | High | Blocked | Constraint error captured per-row but no rollback; prior rows stay committed
45 | Transaction Integrity | Load under DB timeout: if Pulse DB unresponsive >30s, Synapse marks load as failed | No phantom or partial records in Pulse DB; run_manifest shows: load_status='failed', error='DB timeout' | High | Blocked | No statement timeout; watchdog finalizes stuck runs; partial rows remain
46 | Transaction Integrity | Concurrent load from two connectors into shared Pulse table: no deadlock | Both connectors complete successfully; row counts correct; no deadlock exception in DB logs | High | Blocked | Pooled conns + atomic single-statement upsert; no deadlock detect/retry
Monitoring & Tracking
47 | Monitoring & Tracking | Each connector run produces a complete run manifest | Manifest contains: connector_name, run_id, trigger_type, start_time, end_time, records_extracted, records_transformed, records_loaded, error_count | High | Blocked | runs table has id/times/status/counts; missing trigger_type + per-phase counts
48 | Monitoring & Tracking | Run manifests queryable in admin UI with filters by connector, date range, and status | Filter combinations work correctly; results paginated; CSV export of manifest list available | High | Pass | Monitor run list: connector + date-range + status filters, pagination, and CSV export all present and working (15-Jul). Every clause of the expected result met.
49 | Monitoring & Tracking | BAM milestone tracking: extract_complete, transform_complete, load_complete timestamps logged per run | All 3 milestones present in run manifest for successful runs; partial milestones present for failed runs | High | Blocked | No BAM per-phase (extract/transform/load) milestone timestamps
50 | Monitoring & Tracking | Alert triggered on: run failure, DLQ threshold breach, run duration > SLA | Each alert type tested independently; delivery confirmed (email/Slack); alert contains: connector, run_id, detail | High | Blocked | alertDispatcherWorker raises all 3 trigger types into app.alerts - run failure, DLQ-depth breach, and run-duration SLA (15-Jul; thresholds from config, not hardcoded). Gap: no email/Slack delivery; alert payload lacks run_id.
51 | Monitoring & Tracking | Admin dashboard shows connector health RAG, last run time, record counts, next scheduled run | RAG status correct (green=last run ok, amber=last run warning, red=last run failed); all fields populated | High | Pass | Dashboard shows RAG, last run time, record counts, and the computed next scheduled run (nextRunFromCron, 15-Jul). All fields populated.
Performance
52 | Performance | HR full extract: 10,000 employee records extracted and transformed within 5 minutes | Run duration <5 min on integration server; resource utilisation (CPU/RAM) within normal range | High | Blocked | Extract+transform exist; per-row writes; not benchmarked
53 | Performance | All 8 connectors running in parallel complete within 60-minute SLA window | All connectors start within 2 min of scheduled trigger; all complete before SLA window closes | High | Blocked | BullMQ workers + cron enable parallel runs; not benchmarked
54 | Performance | Transform throughput: configured baseline (e.g. 50,000 records/min) achieved | Throughput measured by records_loaded / (load_end - load_start); meets or exceeds baseline | Medium | Blocked | Transform pipeline exists; no batching/bulk; no throughput benchmark
55 | Performance | Pulse DB load: 100,000 rows inserted/updated without lock contention or timeout | No deadlock exceptions; no timeout errors; DB CPU <80% during load; completion within SLA | Medium | Blocked | Writes to Postgres (Pulse DB) but row-by-row upsert, no bulk COPY; unproven at 100k
Security
56 | Security | Source credentials stored in secrets vault; connector retrieves at runtime — not from config file | Config files contain only vault key references; grep of config returns no plaintext passwords or API keys | High | Blocked | Vault real (AES-256); but built-in Jira/SP still read secrets from env/config
57 | Security | Credential rotation: update credential in vault; connector uses new credential on next run without restart | Old credential deactivated in source system; Synapse connector successfully runs with new credential | High | Pass | Admin rotate re-encrypts + re-read each run -> new secret without restart
58 | Security | All connections to source systems and Pulse DB use TLS 1.2 or higher | Network capture or connection log confirms TLS version; no plaintext connections; weak cipher suites rejected | High | Blocked | ssl/encrypt accepted but cert validation disabled; no TLS 1.2+ min enforced
59 | Security | Connector service account has least-privilege access: read-only on sources, write on Pulse staging only | Attempt to write to source system via connector credential returns 403; write to non-staging Pulse tables returns 403 | High | Failed | Single credential per connection; no read-only-source/write-staging separation

## Sheet2
ARCHITECTURE / SCOPE REVIEW - QC Plan vs current Synapse & FSD
'Pulse DB' = the PostgreSQL database of the Pulse product (a normal Synapse destination). Re-assessed below: the data-flow goal matches Synapse / FSD; the real blockers are specific capability gaps, not a different architecture.
A. Written in BizTalk terms, but ALREADY supported by Synapse / FSD (not real deviations)
# | Item | QC plan wording | Synapse / FSD reality | Verdict
1 | "Pulse DB" (destination) | Load data into a "Pulse DB" | Pulse's DB is Postgres; Synapse's Hub writes to Postgres destinations natively (source -> DB) | Supported - not a deviation
2 | 8 business "adapters" | HR / Finance / Sales / etc. adapters | Model each source as a generic connector instance (REST/DB) - exactly the FSD "design once, reuse" model | Supported via config - matches FSD
3 | Staging tables | HR_staging / Finance_staging | Just destination table names; operator points the connector at any table | Supported - not a deviation
B. Genuine capability gaps (missing today - regardless of naming)
# | Gap | What's needed | Synapse today | Severity
4 | Record-level validation + quarantine | Reject/quarantine bad records at runtime | Design-time / config validation only; no per-record reject | Real gap
5 | Content-based routing (dept_code) | Route by reading payload contents | Routes by topic / source only | Real gap
6 | Atomic batch transaction / rollback | All-or-nothing load, rollback on failure | Per-row best-effort writer (high-risk to change) | Real gap (high-risk)
7 | BAM / per-phase run tracking | extract / transform / load milestone timestamps | Runs store start / end / status only | Partial gap
8 | Currency conversion | USD/GBP -> INR at configured rates | No such feature | Feature gap
9 | Least-privilege dual credentials | Read-only source / write-only staging | One credential per connection + AES-256 vault | Feature gap
10 | Runtime schema-drift detection | Detect source change, pause, alert | No schema-watcher | Feature gap
Revised takeaway: the QC plan's goal - feed Pulse's Postgres from multiple business sources - fits Synapse and the FSD. It is NOT a different product; it mainly needs re-wording into Synapse terms plus a short gap-closure list (Section B). Most gaps are simple additions; only #6 (atomic transactions) is high-risk.
C. Closed or advanced by the QC-safe build (Tiers 1-4 + 3b, 15-16 Jul 2026)
# | Item | What shipped | Result | Verdict
48 | Monitor run-list filters + pagination | connector / date-range / status filters, pagination, CSV export | Every expected clause met | Blocked -> PASS
51 | Dashboard next scheduled run | nextRunFromCron computes the next run beside the raw cron | RAG + last run + counts + next run all populated | Blocked -> PASS
7, 8, 9, 10, 12 | Transformation presets | codeMap / parseDate / currency / divide / default presets, backend + config UI in Wizard & Canvas | Transform behaviour verified end-to-end; only the flag/log clause is unmet | Still Blocked - see D
37, 50 | Run-failure / DLQ-depth / SLA alerting | alertDispatcherWorker raises all 3 alert types into app.alerts (config thresholds) | Detection works live (372 DLQ vs threshold 100); delivery does not | Failed -> Blocked
34 | DLQ filter controls | status / topic / destination filters over the existing DLQ list + replay | Filters work; no date filter | Still Blocked
22 | 401 handling | run-failure alert now raised when a run fails on 401 | No 401-specific alert; no auto secret-rotation | Still Blocked
14-21 | 8 business adapters | No code by design - each is a Wizard connection instance of the generic REST/DB connector | Design answer is in place; count-match assertions need the live HRMS/ERP/CRM systems | Still Blocked - needs live systems
D. Why #7 / #8 / #10 / #12 are still Blocked despite working transforms
Each of these expected results ends in a diagnostics clause - 'and are flagged' (#7), 'rejected with error log' (#8), 'result = null, flagged' (#10), 'original null logged in run manifest' (#12). The transform half of every one is now implemented and verified; the flag/log half is not. They are all blocked by a SINGLE missing capability: per-record transform diagnostics written to a run manifest (the same gap as #47 / #49). Build that one thing and four High-priority cases move to Pass together. It was excluded from the QC-safe build because a per-phase run manifest means changing the bus run-recorder.