## Cover
Synapse Integration Platform
Project Plan v3 · Aggressive 2-Month Build + 1-Month UAT
Generated | 2026-06-03
Owner | Kiran Suvarna (Nalashaa)
Delivery window | Dev: 18 May – 17 Jul 2026 · UAT: 20 Jul – 14 Aug 2026 · Go-live: ~15 Aug 2026
Team | 2 full-stack AI engineers (Vibecoding) — Dev A & Dev B. Module ownership, no FE/BE split.
Backend stack | Node.js + Express + TypeScript (kept). LLD's .NET is reference architecture only — no migration.
Code path | D:\Nalashaa_Work\AI_Work\synapse-fullstack
Plan version | v3.0 (supersedes docs/Synapse_Project_Plan_v1.xlsx)
What changed from v1
▸ Backend | Node.js retained. No .NET rewrite — the existing Jira + SharePoint engine stays and we build on it.
▸ Pace | Compressed to 2-month development + 1-month UAT. Aggressive but feasible with Vibecoding velocity.
▸ Team model | 2 full-stack devs own whole modules end-to-end (build + wire + test). No separate FE/BE/QA dev lanes.
▸ New module | Policy-Based Access Control added — company policy -> user subscription -> level of access. High priority.
▸ Already done | SharePoint -> Postgres adapter complete and tested locally. Marked Done in the plan (0 remaining effort).
Scope — modules in this release
Hub engine | Message envelope, bus, router, inbox/outbox/DLQ, retry + circuit breaker (Node/TS per LLD).
Adapters | SharePoint->Postgres (DONE), SharePoint->MSSQL, Jira->SharePoint (harden).
Connection Wizard | Full 6-step builder incl. mapping (Step 4) and test/deploy (Step 6).
Mapping Canvas | Drag-map + AI auto-map (Claude API) with confidence scoring.
Policy-Based Access | Company policy -> user subscription -> enforced access level. JWT + middleware + admin UI.
Monitoring | Health Dashboard, Trading/Message Monitor (full trace), Alerts (in-app + email).
Platform | Connector Studio, Master Entity Catalog (basic), Credential Vault, Scheduler, Audit log, Multi-tenancy.
Tab guide · Status legend
Plan | Module-level tasks. Update Status, %, and Done Date. On-Time auto-calculates.
Milestones | 6 checkpoints M1-M6 with target dates and acceptance criteria.
Sprint Plan | 4 dev sprints + stabilization + UAT. Capacity vs loaded hours auto-calculated.
Risks & Decisions | Top risks and open decisions, kept short.
Not Started
In Progress
Blocked
Done
Effort hours are Vibecoding-adjusted (already discounted for AI-assisted velocity).

## Plan
ID | Sprint | Module | Task | Owner | Effort (h) | Status | % | Start | Due | Done Date | On-Time? | Notes
T-01 | S1 | Hub Engine | MessageEnvelope + SHA-256 checksum + topic model (Node/TS per LLD §6) | Dev A | 24 | Done | 100% | 2026-05-18 | 2026-05-29 | 2026-06-03 |  | COMPLETE (T-01) — immutable envelope + SHA-256 checksum existed; added hub/topic.ts (canonical source.entity.event, validate/parse/build, centralized topicMatches), topic validation + idempotency-key-derived messageId in createEnvelope, router refactor. 59 hub tests pass.
T-02 | S1 | Hub Engine | IntegrationBus + Router + Subscription registry (in-memory queue + fan-out) | Dev A | 24 | Not Started | 0% | 2026-05-18 | 2026-05-29 |  |  | Backpressure via bounded queue.
T-03 | S1 | Hub Engine | Persistence: Inbox / Outbox / DeadLetter / Idempotency tables + repos (Postgres) | Dev A | 20 | Not Started | 0% | 2026-05-18 | 2026-05-29 |  |  | LLD §8 schema, Drizzle.
T-04 | S1 | Reliability | Retry+backoff + circuit breaker + DLQ auto/manual replay | Dev A | 20 | Not Started | 0% | 2026-05-18 | 2026-05-29 |  |  | Per Architecture §11.
T-05 | S1 | Adapter | SharePoint -> Postgres (delta poll, schema introspect, DDL diff/apply, upsert) | Dev B | 0 | Done | 100% | 2026-05-12 | 2026-05-29 | 2026-05-17 |  | COMPLETE — tested locally before kickoff.
T-06 | S1 | Adapter | SharePoint -> MSSQL (extend SP->PG: MERGE upsert + sys.columns introspect) | Dev B | 24 | Done | 100% | 2026-05-18 | 2026-05-29 | 2026-06-02 |  | COMPLETE (T-06) — SqlServerWriter smartUpsert + sys.columns introspect + hub MSSQL endpoints + wizard wiring. Tested.
T-07 | S1 | Frontend | Wire Dashboard + Registry to real APIs (remove mock data) | Dev B | 16 | In Progress | 75% | 2026-05-18 | 2026-05-29 |  |  | T-07 code-complete: integrationMap.js shared mapper, live KPIs/tiles/charts off /api/connected, sample fallback, 0 diagnostics. Pending browser verify for M1.
T-08 | S2 | Wizard | Connection Wizard 6-step backend + Step 4 (mapping) + Step 6 (test/deploy gate) | Dev A | 28 | Not Started | 0% | 2026-06-01 | 2026-06-12 |  |  | Hard test-before-publish gate.
T-09 | S2 | Mapping | Mapping Canvas + AI Auto-Map (Claude API) + confidence badges | Dev B | 30 | Not Started | 0% | 2026-06-01 | 2026-06-12 |  |  | Human-confirm required.
T-10 | S2 | Policy Access | Policy-Based Access Control — data model + policy engine (policies, permissions, subscription) | Dev A | 24 | Not Started | 0% | 2026-06-01 | 2026-06-12 |  |  | NEW. Company policy -> access level.
T-11 | S2 | Frontend | Wire Monitor + Connected + Push to real APIs | Dev B | 18 | Not Started | 0% | 2026-06-01 | 2026-06-12 |  |  | Replace remaining mocks.
T-12 | S2 | Vault | Credential decrypt endpoint + DB-connection credential type + test-connection | Dev A | 12 | Not Started | 0% | 2026-06-01 | 2026-06-12 |  |  | AES-256-GCM in place.
T-13 | S3 | Policy Access | Policy enforcement middleware + JWT login + admin UI (manage policies & user subscriptions) | Dev A | 32 | Not Started | 0% | 2026-06-15 | 2026-06-26 |  |  | NEW. Subscription -> enforced level of access.
T-14 | S3 | Studio | Connector Studio — define / test / publish connector templates (backend + UI) | Dev B | 28 | Not Started | 0% | 2026-06-15 | 2026-06-26 |  |  | Designer workflow.
T-15 | S3 | Alerts | Alerts — failure detection + in-app feed + email dispatch + acknowledge | Dev A | 20 | Not Started | 0% | 2026-06-15 | 2026-06-26 |  |  | Wire dormant queue.
T-16 | S3 | Monitoring | Health Dashboard — real metrics, volume + error charts, drill-down | Dev B | 20 | Not Started | 0% | 2026-06-15 | 2026-06-26 |  |  | Replace hardcoded SVG.
T-17 | S3 | Audit | Audit log — middleware + viewer (ties to Policy module) | Dev A | 14 | Not Started | 0% | 2026-06-15 | 2026-06-26 |  |  | Append-only, before/after diff.
T-18 | S4 | Monitoring | Trading / Message Monitor — full per-message trace + error drill-down + create-task | Dev B | 24 | Not Started | 0% | 2026-06-29 | 2026-07-10 |  |  | Expandable rows, mapping trace.
T-19 | S4 | Catalog | Master Entity Catalog (basic) — entity registry + field-level usage | Dev A | 20 | Not Started | 0% | 2026-06-29 | 2026-07-10 |  |  | Cross-adapter reference.
T-20 | S4 | Platform | Multi-tenancy / org enforcement (row-level org_id, integrated with Policy) | Dev A | 16 | Not Started | 0% | 2026-06-29 | 2026-07-10 |  |  | Data isolation.
T-21 | S4 | Scheduler | Scheduler wire + cron builder UI (BullMQ repeatable jobs) | Dev B | 16 | Not Started | 0% | 2026-06-29 | 2026-07-10 |  |  | Next-run preview.
T-22 | S4 | Adapter | Jira -> SharePoint parity verify + harden | Dev B | 12 | Not Started | 0% | 2026-06-29 | 2026-07-10 |  |  | Existing engine regression.
T-23 | S4 | Integration | End-to-end integration testing + bug bash (all modules) | Both | 24 | Not Started | 0% | 2026-06-29 | 2026-07-10 |  |  | Feature-complete gate.
T-24 | Stab | Hardening | Security review (vault, policy enforcement, OWASP) + perf test (parallel workers) | Both | 20 | Not Started | 0% | 2026-07-13 | 2026-07-17 |  |  | Pre-UAT gate.
T-25 | Stab | Hardening | Regression suite + smoke + fixes | Both | 16 | Not Started | 0% | 2026-07-13 | 2026-07-17 |  |  | Stabilize.
T-26 | Stab | Deploy | Deploy to UAT environment (Docker) + smoke + runbook | Dev A | 12 | Not Started | 0% | 2026-07-13 | 2026-07-17 |  |  | Code freeze.
T-27 | UAT | UAT | UAT planning + scenarios + test-data setup | BA/QA | 24 | Not Started | 0% | 2026-07-20 | 2026-08-14 |  |  | Scripts per module.
T-28 | UAT | UAT | UAT cycle 1 execution | QA + Stakeholders | 40 | Not Started | 0% | 2026-07-20 | 2026-08-14 |  |  | Log defects.
T-29 | UAT | UAT | Defect triage + fixes (cycle 1) | Both | 40 | Not Started | 0% | 2026-07-20 | 2026-08-14 |  |  | Devs on standby.
T-30 | UAT | UAT | UAT cycle 2 + regression | QA | 24 | Not Started | 0% | 2026-07-20 | 2026-08-14 |  |  | Verify fixes.
T-31 | UAT | UAT | UAT signoff + go-live readiness | BA + Stakeholders | 8 | Not Started | 0% | 2026-07-20 | 2026-08-14 |  |  | Final acceptance.
S1 subtotal
S2 subtotal
S3 subtotal
S4 subtotal
Stab subtotal
UAT subtotal
GRAND TOTAL (hrs)

## Milestones
ID | Milestone | Target Date | Status | Owner | Acceptance Criteria | Actual Date | Slip (days)
M1 | Hub engine live + adapters working + Dashboard/Registry on real data | 2026-05-29 | Not Started | Dev A | Message flows Inbox->Bus->Router->Outbox; DLQ on forced failure; SP->PG + SP->MSSQL write live; Dashboard & Registry show real runs.
M2 | Connection Wizard end-to-end + Mapping Canvas with AI auto-map | 2026-06-12 | Not Started | Dev A | Operator builds an integration through all 6 steps; AI auto-map suggests with confidence; test-before-publish gate enforced.
M3 | Policy-Based Access Control GA + Alerts + Health Dashboard | 2026-06-26 | Not Started | Dev A | Company policy -> user subscription -> enforced access level verified across roles; failure alert reaches in-app + email; Health Dashboard live on real metrics.
M4 | Feature-complete — all modules integrated, E2E passing | 2026-07-10 | Not Started | Both | All Plan modules Done; end-to-end test suite green; no open Sev-1/2 defects.
M5 | Code freeze — security/perf cleared, deployed to UAT | 2026-07-17 | Not Started | Both | Security review passed (vault + policy enforcement); perf test meets target; build deployed to UAT env with smoke pass + runbook.
M6 | UAT signoff & go-live readiness | 2026-08-14 | Not Started | BA + Stakeholders | UAT cycles 1-2 complete; all signoff scenarios passed; go-live checklist approved.
Formulas:
Slip (days) = IF([Actual Date]="","",NETWORKDAYS([Target Date],[Actual Date])-1)

## Sprint Plan
Sprint | Start | End | Goal | Capacity (h) | Loaded (h) | Utilization | Milestone
S1 | 2026-05-18 | 2026-05-29 | Hub engine + reliability · SP->MSSQL adapter · Dashboard/Registry wired | 144 |  |  | M1
S2 | 2026-06-01 | 2026-06-12 | Connection Wizard · Mapping Canvas + AI auto-map · Policy model · Vault | 144 |  |  | M2
S3 | 2026-06-15 | 2026-06-26 | Policy enforcement + admin UI · Connector Studio · Alerts · Health Dashboard · Audit | 144 |  |  | M3
S4 | 2026-06-29 | 2026-07-10 | Trading Monitor · Entity Catalog · Multi-tenancy · Scheduler · E2E bug bash | 144 |  |  | M4
Stab | 2026-07-13 | 2026-07-17 | Security + perf review · regression · deploy to UAT (code freeze) | 72 |  |  | M5
UAT | 2026-07-20 | 2026-08-14 | UAT cycles 1-2 · defect fixing · signoff · go-live readiness | 240 |  |  | M6
Capacity: 2 devs × ~36 productive h/week (Vibecoding) = 144 h per 2-week sprint. Stab = 1 week. UAT capacity blends devs + QA + stakeholders.

## Risks & Decisions
ID | Type | Item | Likelihood | Impact | Mitigation / Action | Owner | Due | Status
R1 | Risk | Two-month window is aggressive; any module slip cascades | H | H | Weekly burn-down vs Sprint capacity; cut Catalog/Studio to 'basic' first if behind; protect Policy module + adapters. | Kiran | 2026-05-29 | Open
R2 | Risk | Policy-Based Access is new and security-sensitive | M | H | Spike the policy model in S2 before enforcement in S3; security review at Stab; least-privilege defaults. | Dev A | 2026-06-12 | Open
R3 | Risk | Vibecoding velocity assumption (144h/sprint) may not hold for hub internals | M | M | Track actual vs planned each sprint; rebaseline after S1; keep S4 light as buffer. | Kiran | 2026-05-29 | Open
R4 | Risk | Frontend mock->real swap surfaces API contract gaps | M | M | Generate TS types from backend DTOs; wire one screen end-to-end in S1 as the pattern. | Dev B | 2026-05-29 | Open
R5 | Risk | Playwright/MFA adapters fragile to client config | M | M | Smoke each adapter after deploy; session persistence + re-login fallback. | Dev B | 2026-07-17 | Open
R6 | Risk | UAT defects exceed 1-month fix capacity | M | H | Bug-bash in S4 before freeze; both devs reserved for UAT defect fixing; triage Sev-1/2 only for go-live. | Both | 2026-08-07 | Open
D1 | Decision | AI provider for auto-mapping (Claude / OpenAI / local) | — | M | Default Claude API; confirm by S2 start on cost × accuracy. | Dev B | 2026-06-01 | Open
D2 | Decision | Policy model — RBAC roles vs full ABAC (attribute) policies | — | H | Recommend policy = named permission-set users subscribe to (RBAC+scope). Confirm S2. | Kiran | 2026-06-01 | Open
D3 | Decision | UAT environment host — local box / VM / cloud | — | M | Pick by S3 so Stab deploy is ready. Default: in-office VM + Docker. | Dev A | 2026-06-15 | Open
D4 | Decision | Next adapters after MSSQL (priority order) | — | M | Confirm with stakeholders by M1 demo. | Kiran | 2026-05-29 | Open