## Cover
Synapse / XnHub Integration Platform
Project Plan v2 · WBS · Milestones · Effort · Sprints · Risks
Generated | 2026-05-19
Owner | Kiran Suvarna (Nalashaa)
Client / Audience | Internal — Nalashaa Org-Level Integration Platform
Code path | D:\Nalashaa_Work\AI_Work\synapse-fullstack
Source docs | Synapse Architecture v4 · Synapse LLD · Developer Handbook · XnHub Product Charter v2
Plan version | v2.0
Assumptions (redirect any of these and the plan recalculates)
▸ Backend stack | .NET 8 (matches Architecture / LLD / Handbook verbatim). Python (FastAPI + Celery) is the documented alternative — swap the BE owner-role tasks if changed.
▸ Scope | MVP (Phase 1) + Phase 2 (Intelligence & Monitoring) from XnHub Charter §8. Phase 3 / 4 tracked as roadmap only.
▸ Vibecoding multiplier | 0.5x of traditional hand-coded estimate. Vibe Hours column = Trad Hours × 0.5. Change cell B3 on the WBS tab to re-flow the entire plan.
▸ Team | 1 BA · 1 FE Dev · 1 BE Dev · 1 QA · 0.25 DevOps. Capacity baseline: 160 hrs/person/month (8 hrs × 20 working days).
▸ Cadence | 10 sprints of 2 weeks. Sprint 0 starts Mon 2026-05-25. Phase 2 UAT signoff target Fri 2026-11-13.
▸ Frontend | React 19 + Vite at packages/frontend is KEPT AS-IS. Backend rewrite only. UI work = wire mocks → real API + new Login/Studio backend.
Existing codebase audit (PRODUCT_STATUS.md, 2026-04-22)
▸ Frontend (React 19 + Vite) | 13 pages — all COMPLETE on UI. All use MOCK DATA except Wizard Step 2 (real API). Login screen NOT BUILT.
▸ Backend (Node/Express) | FULLY BUILT: Jira (Red Gold REST + Flatiron Playwright/MFA), SharePoint Push (Graph API), 35-field mapper, AES-256-GCM vault, Scheduler (BullMQ), Sync delta, Run mgmt.
▸ Backend gaps | NOT BUILT: Auth/JWT, Multi-tenancy enforcement, Alerts dispatch, Audit logging, Connector Studio backend, AI auto-map, Trading Console drill-down, Master Entity Catalog.
▸ Migration approach | Port FULLY BUILT modules first (Sprints 1-3) → reach parity with Node version (M2) → then build NOT BUILT modules on top of new .NET hub.
Tab guide
WBS | Every task. Update Status, % Complete, and Delivered Date per task. On-Time and Days Slip auto-calculate.
Milestones | 10 milestones (M0–M9) with target dates. Update Actual Date when achieved; Slip Days auto-calculates.
Effort Summary | Live pivot of hours by Phase × Role. Reads directly from WBS — never edit cells here, edit WBS.
Sprint Plan | 10 sprints with goals, demo items, capacity, and loaded utilization. Loaded Hours and Utilization auto-calculate.
Risks & Open | Charter §11 risks + .NET migration risks + 3 open decisions. Update Status as items close.
Status legend (matches WBS conditional formatting)
Not Started
In Progress
Blocked
Done
Cancelled

## WBS
Vibe multiplier: | 0.5 | ← change this cell to re-flow all Vibe Hours
WBS ID | Phase | Workstream | Task | Owner Role | Trad Hours | Vibe Hours | Sprint | Status | % Complete | Original ETA | Current ETA | Delivered Date | On-Time? | Days Slip | Notes / Dependencies
W-001 | Phase 0 | Setup | Stand up .NET 8 solution skeleton (Synapse.Core, Synapse.Host, Synapse.Tests) per LLD §2.1 | BE | 16 |  | 0 | Not Started | 0% | 2026-06-04 | 2026-06-04 |  |  |  | Branch off main; reference LLD project dependency graph.
W-002 | Phase 0 | Setup | Add Synapse.Connectors.Jira and Synapse.Connectors.SharePoint empty projects + ProjectReferences | BE | 4 |  | 0 | Not Started | 0% | 2026-06-04 | 2026-06-04 |  |  |  | Mirror Node module boundaries.
W-003 | Phase 0 | Setup | Drizzle → EF Core schema migration (13 tables → C# entities, snake_case keep) | BE | 24 |  | 0 | Not Started | 0% | 2026-06-04 | 2026-06-04 |  |  |  | Preserve org_id everywhere; keep app + jira_data schemas.
W-004 | Phase 0 | DevOps | docker-compose: keep Postgres + Redis, replace Node service with .NET API service | DevOps | 8 |  | 0 | Not Started | 0% | 2026-06-04 | 2026-06-04 |  |  |  | Two service blocks: api + playwright-worker.
W-005 | Phase 0 | DevOps | GitHub Actions CI: dotnet build + test + Playwright install + frontend build | DevOps | 12 |  | 0 | Not Started | 0% | 2026-06-04 | 2026-06-04 |  |  |  | Cache nuget + npm; matrix linux + windows.
W-006 | Phase 0 | DevOps | Dockerfile for .NET API + Dockerfile.playwright for browser worker (separate image) | DevOps | 8 |  | 0 | Not Started | 0% | 2026-06-04 | 2026-06-04 |  |  |  | Per CLAUDE.md §10 — Playwright workers need browser binaries.
W-007 | Phase 0 | BA | Baseline requirements doc — map Charter §5 modules to MVP+Phase 2 backlog with acceptance criteria | BA | 16 |  | 0 | Not Started | 0% | 2026-06-04 | 2026-06-04 |  |  |  | Single source of truth for sprint planning.
W-008 | Phase 0 | BA | Acceptance criteria template (Given/When/Then) + UAT script template | BA | 8 |  | 0 | Not Started | 0% | 2026-06-04 | 2026-06-04 |  |  |  | Reuse across all sprint demos.
W-009 | Phase 0 | QA | Test strategy doc — unit (xUnit) / integration / E2E (Playwright) / perf / security split per Handbook §9 | QA | 12 |  | 0 | Not Started | 0% | 2026-06-04 | 2026-06-04 |  |  |  | Sets the test pyramid.
W-010 | Phase 0 | Setup | Dev environment + onboarding doc (refresh existing CLAUDE.md for .NET path) | BE | 8 |  | 0 | Not Started | 0% | 2026-06-04 | 2026-06-04 |  |  |  | Replace Node-specific steps.
W-011 | Phase 1 | Hub Core | Implement ISourceConnector, IDestinationConnector, ITransformStep interfaces (LLD §6) | BE | 16 |  | 1 | Not Started | 0% | 2026-06-18 | 2026-06-18 |  |  |  | Three interfaces — the only contract surface.
W-012 | Phase 1 | Hub Core | MessageEnvelope record + SHA-256 ComputeChecksum + IsChecksumValid (LLD §6, Handbook §4.1) | BE | 16 |  | 1 | Not Started | 0% | 2026-06-18 | 2026-06-18 |  |  |  | Immutable record; thread-safe Payload Clone().
W-013 | Phase 1 | Hub Core | IntegrationBus + bounded System.Threading.Channels intake + per-subscription channels | BE | 24 |  | 1 | Not Started | 0% | 2026-06-18 | 2026-06-18 |  |  |  | Backpressure naturally via Channel.Writer.WriteAsync.
W-014 | Phase 1 | Hub Core | SubscriptionRegistry loader (subscriptions.json) + Subscription model | BE | 16 |  | 1 | Not Started | 0% | 2026-06-18 | 2026-06-18 |  |  |  | Immutable post-load.
W-015 | Phase 1 | Persistence | EF Core HubDbContext + 4 entity types: InboxEntry, OutboxEntry, DeadLetterEntry, IdempotencyEntry | BE | 20 |  | 1 | Not Started | 0% | 2026-06-18 | 2026-06-18 |  |  |  | Schema per LLD §8.
W-016 | Phase 1 | Persistence | InboxRepository + OutboxRepository + DeadLetterRepository + IdempotencyRepository | BE | 24 |  | 1 | Not Started | 0% | 2026-06-18 | 2026-06-18 |  |  |  | Scoped lifetime; IDbContextFactory.
W-017 | Phase 1 | QA | Unit tests: envelope checksum round-trip, channel backpressure, repository upsert | QA | 16 |  | 1 | Not Started | 0% | 2026-06-18 | 2026-06-18 |  |  |  | Cover all 4 abstractions before connectors land.
W-018 | Phase 1 | BA | Sprint 1 user-story refinement + acceptance criteria for hub core | BA | 10 |  | 1 | Not Started | 0% | 2026-06-18 | 2026-06-18 |  |  |  | Hub-engine stories: "as a router, I can fan-out to N subs".
W-019 | Phase 1 | Hub Core | RouterService (BackgroundService): reads intake channel, fans out to subscription channels | BE | 20 |  | 2 | Not Started | 0% | 2026-07-02 | 2026-07-02 |  |  |  | Single loop; sole intake reader.
W-020 | Phase 1 | Hub Core | SubscriptionWorkerOrchestrator + SubscriptionWorker per Subscription (Serial mode first) | BE | 24 |  | 2 | Not Started | 0% | 2026-07-02 | 2026-07-02 |  |  |  | Other modes deferred until Phase 2 perf.
W-021 | Phase 1 | Hub Core | TransformPipeline executor (LLD §4.6) — chain ITransformStep by config order | BE | 16 |  | 2 | Not Started | 0% | 2026-07-02 | 2026-07-02 |  |  |  | Unknown StepId: warn + skip.
W-022 | Phase 1 | Reliability | Polly ResiliencePipeline per destination: retry 3x exp+jitter + circuit breaker 0.5/30s + bulkhead | BE | 16 |  | 2 | Not Started | 0% | 2026-07-02 | 2026-07-02 |  |  |  | Per LLD §11.1 + Architecture §11.
W-023 | Phase 1 | Reliability | Dead Letter Queue auto-replay BackgroundService (5-min scan) + Poisoned state alerting | BE | 20 |  | 2 | Not Started | 0% | 2026-07-02 | 2026-07-02 |  |  |  | Per Architecture §11.2.
W-024 | Phase 1 | Reliability | Manual + bulk DLQ replay endpoints | BE | 10 |  | 2 | Not Started | 0% | 2026-07-02 | 2026-07-02 |  |  |  | POST /hub/dlq/{id}/replay + bulk by destination.
W-025 | Phase 1 | Hub Core | DI wiring: ServiceCollectionExtensions.AddSynapseCore() per LLD §7 table | BE | 10 |  | 2 | Not Started | 0% | 2026-07-02 | 2026-07-02 |  |  |  | Lifetimes per LLD table 5.
W-026 | Phase 1 | QA | Integration tests: end-to-end fake source → router → transform → fake destination → inbox=Done | QA | 20 |  | 2 | Not Started | 0% | 2026-07-02 | 2026-07-02 |  |  |  | Use Handbook §9.2 pipeline fakes pattern.
W-027 | Phase 1 | BA | Sprint 2 demo prep + stakeholder walkthrough of hub engine | BA | 8 |  | 2 | Not Started | 0% | 2026-07-02 | 2026-07-02 |  |  |  | Demo M1 milestone candidate.
W-028 | Phase 1 | Connector | Port RedGoldApiClient (REST + Basic Auth + p-limit) to .NET HttpClient + Polly | BE | 24 |  | 3 | Not Started | 0% | 2026-07-16 | 2026-07-16 |  |  |  | Direct translation; preserve pagination loop.
W-029 | Phase 1 | Connector | Port RedGoldDataExtractor JQL strategy + worklog expand → MessageEnvelope publish | BE | 20 |  | 3 | Not Started | 0% | 2026-07-16 | 2026-07-16 |  |  |  | Status-changed JQL; worklog within report period.
W-030 | Phase 1 | Connector | Port FlatironScraper to Microsoft.Playwright (.NET) + TOTP via Otp.NET | BE | 32 |  | 3 | Not Started | 0% | 2026-07-16 | 2026-07-16 |  |  |  | MFA + storageState persistence (8hr); headed for debug.
W-031 | Phase 1 | Connector | Port FlatironDataExtractor label-pattern fetch (patch_*, tempapp_*, nalashaa_*) + Testmo session | BE | 24 |  | 3 | Not Started | 0% | 2026-07-16 | 2026-07-16 |  |  |  | Per CLAUDE.md §5.2 label conventions.
W-032 | Phase 1 | Connector | Port JiraTicketNormalizer (Flatiron + Red Gold → NormalizedJiraTicket) | BE | 16 |  | 3 | Not Started | 0% | 2026-07-16 | 2026-07-16 |  |  |  | Pure mapping; covered by fixtures.
W-033 | Phase 1 | Connector | Port SharePoint OAuth2 client-credentials auth + token cache + Graph site/list resolve | BE | 16 |  | 3 | Not Started | 0% | 2026-07-16 | 2026-07-16 |  |  |  | Microsoft.Graph SDK.
W-034 | Phase 1 | Connector | Port SharePoint Push (create/update list items + 3-layer dedup + batch=20 + progress) | BE | 24 |  | 3 | Not Started | 0% | 2026-07-16 | 2026-07-16 |  |  |  | Preserve pushLog → jiraItemCache → SP query order.
W-035 | Phase 1 | Connector | Port 35-field Jira→SharePoint mapper + derived fields (CycleTimeDays, IsOverdue, etc.) | BE | 20 |  | 3 | Not Started | 0% | 2026-07-16 | 2026-07-16 |  |  |  | Bring fixtures from Node tests.
W-036 | Phase 1 | QA | Live integration test: Red Gold credential → real ticket pull → SharePoint test list write | QA | 16 |  | 3 | Not Started | 0% | 2026-07-16 | 2026-07-16 |  |  |  | Requires test Jira + SP tenant.
W-037 | Phase 1 | QA | Live integration test: Flatiron MFA flow with headed Playwright + session restore | QA | 16 |  | 3 | Not Started | 0% | 2026-07-16 | 2026-07-16 |  |  |  | Capture screenshots on failure.
W-038 | Phase 1 | BA | Acceptance test for Jira → SharePoint parity (records-in = records-out, no dupes) | BA | 10 |  | 3 | Not Started | 0% | 2026-07-16 | 2026-07-16 |  |  |  | Defines M2 milestone gate.
W-039 | Phase 1 | Vault | Port CredentialService (AES-256-GCM, per-org key) to .NET — KeyDerivation.HKDF | BE | 16 |  | 4 | Not Started | 0% | 2026-07-30 | 2026-07-30 |  |  |  | Encrypted payload shape unchanged.
W-040 | Phase 1 | Vault | Credentials API: POST /credentials, GET /credentials, GET /credentials/:id (metadata only) | BE | 12 |  | 4 | Not Started | 0% | 2026-07-30 | 2026-07-30 |  |  |  | Never return plaintext.
W-041 | Phase 1 | Scheduler | Port SchedulerService from BullMQ → Quartz.NET cron with dynamic CRUD | BE | 24 |  | 4 | Not Started | 0% | 2026-07-30 | 2026-07-30 |  |  |  | Persistent job store on Postgres.
W-042 | Phase 1 | Runtime | Run management: RunRecord + status state machine (pending/running/success/error) | BE | 16 |  | 4 | Not Started | 0% | 2026-07-30 | 2026-07-30 |  |  |  | Preserve records_in/records_out semantics.
W-043 | Phase 1 | Runtime | Worker hosting: HostedService that owns Quartz + Playwright queues (concurrency=1 for browser) | BE | 20 |  | 4 | Not Started | 0% | 2026-07-30 | 2026-07-30 |  |  |  | Per CLAUDE.md §2.3.
W-044 | Phase 1 | API | API parity: /integrations, /jira, /sharepoint, /push, /sync, /connected — Express routes → ASP.NET | BE | 32 |  | 4 | Not Started | 0% | 2026-07-30 | 2026-07-30 |  |  |  | Zod → FluentValidation. Same response envelope.
W-045 | Phase 1 | Security | RBAC schema (roles enum) + users/orgs seed + JWT bearer middleware (org_id claim) | BE | 20 |  | 4 | Not Started | 0% | 2026-07-30 | 2026-07-30 |  |  |  | Cookie + Bearer; refresh tokens.
W-046 | Phase 1 | Security | Row-level multi-tenancy: query filters by org_id on every entity (global EF filter) | BE | 16 |  | 4 | Not Started | 0% | 2026-07-30 | 2026-07-30 |  |  |  | HasQueryFilter pattern.
W-047 | Phase 1 | Alerts | Basic alerts: failure detection in BackgroundService → write Alert row (in-app only) | BE | 16 |  | 4 | Not Started | 0% | 2026-07-30 | 2026-07-30 |  |  |  | Email/Slack deferred to Phase 2.
W-048 | Phase 1 | Audit | Audit log middleware: write to audit_log on auth-sensitive routes (CRUD vault/integrations/users) | BE | 12 |  | 4 | Not Started | 0% | 2026-07-30 | 2026-07-30 |  |  |  | Append-only; before/after diff.
W-049 | Phase 1 | QA | Unit tests: AES-256-GCM round-trip + JWT claims + RLS query filter | QA | 16 |  | 4 | Not Started | 0% | 2026-07-30 | 2026-07-30 |  |  |  | Wrong-key throws, expired token rejects.
W-050 | Phase 1 | QA | API contract tests vs old Node API (parity oracle) | QA | 20 |  | 4 | Not Started | 0% | 2026-07-30 | 2026-07-30 |  |  |  | Postman/RestAssured replay.
W-051 | Phase 1 | BA | RBAC permission matrix sign-off (Admin / Designer / Operator / Viewer per Charter §5.8.2 table) | BA | 10 |  | 4 | Not Started | 0% | 2026-07-30 | 2026-07-30 |  |  |  | Permission grid is the source of truth.
W-052 | Phase 1 | Frontend | Login screen + Auth.js integration (calls .NET JWT endpoint, stores in HttpOnly cookie) | FE | 16 |  | 5 | Not Started | 0% | 2026-08-13 | 2026-08-13 |  |  |  | First time real auth ships.
W-053 | Phase 1 | Frontend | Wire Dashboard: remove mockDashboardTiles, fetch /integrations + /runs, real KPI cards | FE | 12 |  | 5 | Not Started | 0% | 2026-08-13 | 2026-08-13 |  |  |  | Add loading + empty states.
W-054 | Phase 1 | Frontend | Wire Registry: real /integrations list + sparklines from /runs | FE | 10 |  | 5 | Not Started | 0% | 2026-08-13 | 2026-08-13 |  |  |  | Replace mock integrations.js.
W-055 | Phase 1 | Frontend | Wire Monitor: real /runs + expandable row with /runs/:id detail (payload + mapping trace) | FE | 14 |  | 5 | Not Started | 0% | 2026-08-13 | 2026-08-13 |  |  |  | Largest table — paginate.
W-056 | Phase 1 | Frontend | Wire Alerts: real /alerts list + acknowledge action POST /alerts/:id/ack | FE | 8 |  | 5 | Not Started | 0% | 2026-08-13 | 2026-08-13 |  |  |  | Severity sort.
W-057 | Phase 1 | Frontend | Wire Vault: real /credentials (masked) + add/rotate flow with eye-icon reveal (10s auto-hide) | FE | 12 |  | 5 | Not Started | 0% | 2026-08-13 | 2026-08-13 |  |  |  | Per Charter §5.9.
W-058 | Phase 1 | Frontend | Wire Connected: real /connected list + schedule modal hooked to PATCH schedule | FE | 10 |  | 5 | Not Started | 0% | 2026-08-13 | 2026-08-13 |  |  |  | Cron presets unchanged.
W-059 | Phase 1 | Frontend | Wire Push: real POST /push call + dedup modal from server response | FE | 10 |  | 5 | Not Started | 0% | 2026-08-13 | 2026-08-13 |  |  |  | Surface server-side dedup.
W-060 | Phase 1 | Frontend | Wire Admin: real /users CRUD + role edit + activate/deactivate | FE | 12 |  | 5 | Not Started | 0% | 2026-08-13 | 2026-08-13 |  |  |  | Soft delete only.
W-061 | Phase 1 | Frontend | Wizard Step 4 (Mapping): replace redirect stub with inline canvas + commit to integration | FE | 16 |  | 5 | Not Started | 0% | 2026-08-13 | 2026-08-13 |  |  |  | Largest wizard fix.
W-062 | Phase 1 | Frontend | Wizard Step 6 (Test & Deploy): actual test execution via /integrations/:id/run + publish flow | FE | 12 |  | 5 | Not Started | 0% | 2026-08-13 | 2026-08-13 |  |  |  | Hard gate per Charter §5.2.
W-063 | Phase 1 | Frontend | Studio page: enable Test Connection + Publish buttons + wire to /connectors endpoints | FE | 16 |  | 5 | Not Started | 0% | 2026-08-13 | 2026-08-13 |  |  |  | Companion backend in BE row below.
W-064 | Phase 1 | Frontend | Charts: replace hardcoded SVG with Recharts wired to /runs aggregates (volume + error trend) | FE | 14 |  | 5 | Not Started | 0% | 2026-08-13 | 2026-08-13 |  |  |  | Use SIS-P1 5-second rule layout.
W-065 | Phase 1 | Frontend | Loading states + error toasts + Zod form validation across all pages | FE | 16 |  | 5 | Not Started | 0% | 2026-08-13 | 2026-08-13 |  |  |  | Cross-cutting cleanup.
W-066 | Phase 1 | Backend | Connectors CRUD API (/connectors POST/GET/PUT/publish) for Studio page | BE | 20 |  | 5 | Not Started | 0% | 2026-08-13 | 2026-08-13 |  |  |  | Use existing connectors table.
W-067 | Phase 1 | QA | E2E test suite (Playwright Test): login → create integration → run → view in monitor | QA | 24 |  | 5 | Not Started | 0% | 2026-08-13 | 2026-08-13 |  |  |  | Per CLAUDE.md §12.
W-068 | Phase 1 | QA | Regression: full Jira→SP run, schedule fire, vault rotate, dedup behaviour | QA | 16 |  | 5 | Not Started | 0% | 2026-08-13 | 2026-08-13 |  |  |  | Smoke + critical paths.
W-069 | Phase 1 | QA | Security review: OWASP top 10 + credential vault threat model + JWT settings | QA | 16 |  | 5 | Not Started | 0% | 2026-08-13 | 2026-08-13 |  |  |  | Hard gate before UAT.
W-070 | Phase 1 | BA | MVP UAT planning + test scenarios + stakeholder schedule | BA | 16 |  | 5 | Not Started | 0% | 2026-08-13 | 2026-08-13 |  |  |  | Coordinate with all module owners.
W-071 | Phase 1 | BA | MVP UAT execution + signoff coordination | BA | 20 |  | 5 | Not Started | 0% | 2026-08-13 | 2026-08-13 |  |  |  | M5 milestone owner.
W-072 | Phase 1 | DevOps | Stage env deploy: containers + Postgres + Redis + smoke health check | DevOps | 12 |  | 5 | Not Started | 0% | 2026-08-13 | 2026-08-13 |  |  |  | Stage = production rehearsal.
W-073 | Phase 1 | DevOps | Structured logging (Serilog) + correlation IDs + log shipping | DevOps | 8 |  | 5 | Not Started | 0% | 2026-08-13 | 2026-08-13 |  |  |  | Per Architecture §6 envelope CorrelationId.
W-074 | Phase 2 | AI | AI Auto-Mapping service: schema-aware prompt to Claude API + confidence score per pair | BE | 32 |  | 6 | Not Started | 0% | 2026-08-27 | 2026-08-27 |  |  |  | Per Charter §5.3.2 + D2 decision.
W-075 | Phase 2 | AI | Persist suggestion review state (suggested / confirmed / rejected / adjusted) per integration | BE | 12 |  | 6 | Not Started | 0% | 2026-08-27 | 2026-08-27 |  |  |  | New table or JSONB on integration row.
W-076 | Phase 2 | AI | NL Transformation builder: NL → expression (Roslyn script for .NET; sandboxed) | BE | 32 |  | 6 | Not Started | 0% | 2026-08-27 | 2026-08-27 |  |  |  | Sandboxed compilation; allow-list types.
W-077 | Phase 2 | Frontend | Mapping Canvas: AI Auto-Map button + dashed-line suggestions + confidence badges + confirm/reject | FE | 24 |  | 6 | Not Started | 0% | 2026-08-27 | 2026-08-27 |  |  |  | Per Charter §5.3.2 visual spec.
W-078 | Phase 2 | Frontend | Transformation slide-up panel: presets + NL input + AI-generated script preview | FE | 20 |  | 6 | Not Started | 0% | 2026-08-27 | 2026-08-27 |  |  |  | Per Charter §5.3.3.
W-079 | Phase 2 | QA | AI test set: 50-pair mapping fixtures, measure auto-map accuracy vs >70% target | QA | 16 |  | 6 | Not Started | 0% | 2026-08-27 | 2026-08-27 |  |  |  | Charter §10 success metric.
W-080 | Phase 2 | BA | AI mapping acceptance criteria + fallback rules (always require human confirmation) | BA | 10 |  | 6 | Not Started | 0% | 2026-08-27 | 2026-08-27 |  |  |  | Charter §11 risk mitigation.
W-081 | Phase 2 | Monitoring | Trading Network Console backend: /messages query with payload + transform trace per message | BE | 24 |  | 7 | Not Started | 0% | 2026-09-10 | 2026-09-10 |  |  |  | Heavy read — paginate aggressively.
W-082 | Phase 2 | Frontend | Trading Console UI: table + expandable rows (JSON syntax-highlight, mapping trace, error stack) | FE | 24 |  | 7 | Not Started | 0% | 2026-09-10 | 2026-09-10 |  |  |  | Per Charter §5.6.
W-083 | Phase 2 | Monitoring | Health Dashboard backend: /metrics aggregations (per-adapter status, volume, error trend) | BE | 20 |  | 7 | Not Started | 0% | 2026-09-10 | 2026-09-10 |  |  |  | Materialized view if needed.
W-084 | Phase 2 | Frontend | Health Dashboard UI: adapter tiles + volume stacked-bar + error trend line + drill-down | FE | 24 |  | 7 | Not Started | 0% | 2026-09-10 | 2026-09-10 |  |  |  | Real data; replace mock dashboardTiles.js.
W-085 | Phase 2 | Frontend | Real-time refresh (SSE) for Trading Console + Health Dashboard pages | FE | 16 |  | 7 | Not Started | 0% | 2026-09-10 | 2026-09-10 |  |  |  | Pause button per Charter §5.6.
W-086 | Phase 2 | QA | Perf test: 4-worker Parallel mode @ 100 msg/s for 1 hour — verify 3x throughput vs Serial | QA | 16 |  | 7 | Not Started | 0% | 2026-09-10 | 2026-09-10 |  |  |  | Per Architecture §7.1 claim.
W-087 | Phase 2 | QA | Trading Console: payload search + filter combo regression | QA | 10 |  | 7 | Not Started | 0% | 2026-09-10 | 2026-09-10 |  |  |  | Common ops use case.
W-088 | Phase 2 | BA | Demo: Trading Console + Health Dashboard to stakeholders (M7 milestone) | BA | 8 |  | 7 | Not Started | 0% | 2026-09-10 | 2026-09-10 |  |  |  | Sprint 7 demo.
W-089 | Phase 2 | Catalog | Master Entity Catalog backend: entity registry + cross-adapter usage + field-level stats | BE | 28 |  | 8 | Not Started | 0% | 2026-09-24 | 2026-09-24 |  |  |  | Per Charter §5.5.
W-090 | Phase 2 | Frontend | Master Entity Catalog UI: tree nav + field table + usage bars + cross-reference links | FE | 24 |  | 8 | Not Started | 0% | 2026-09-24 | 2026-09-24 |  |  |  | Replace catalog page hardcoded data.
W-091 | Phase 2 | Connector | Generic Database connector (SQL Server + Postgres source/dest with introspection) | BE | 32 |  | 8 | Not Started | 0% | 2026-09-24 | 2026-09-24 |  |  |  | Per Charter §5.1.1 DB category.
W-092 | Phase 2 | Connector | File Share connector (CSV/Excel source/dest with delimiter + sheet picker) | BE | 24 |  | 8 | Not Started | 0% | 2026-09-24 | 2026-09-24 |  |  |  | Per Charter Phase 2 scope.
W-093 | Phase 2 | Scraping | Apify cloud actor connector (config + run-trigger + result fetch) | BE | 20 |  | 8 | Not Started | 0% | 2026-09-24 | 2026-09-24 |  |  |  | Per Charter §5.1.1 web scraping (a).
W-094 | Phase 2 | Scraping | Playwright Automation connector (recorded/scripted flow runner + JSON result mapper) | BE | 24 |  | 8 | Not Started | 0% | 2026-09-24 | 2026-09-24 |  |  |  | Per Charter §5.1.1 web scraping (b).
W-095 | Phase 2 | Scraping | Scraping connector breakage alert (screenshot-diff on Playwright failure) | BE | 10 |  | 8 | Not Started | 0% | 2026-09-24 | 2026-09-24 |  |  |  | Charter §5.11.1.
W-096 | Phase 2 | QA | Connector regression: each new connector → source → transform → dest happy path + error path | QA | 24 |  | 8 | Not Started | 0% | 2026-09-24 | 2026-09-24 |  |  |  | 4 new connectors × 2 paths each.
W-097 | Phase 2 | BA | Entity merge UX spec + impact-analysis acceptance criteria | BA | 12 |  | 8 | Not Started | 0% | 2026-09-24 | 2026-09-24 |  |  |  | Defer merge impl to Phase 3.
W-098 | Phase 2 | Alerts | Email alert dispatcher (SendGrid) + per-user notification prefs (immediate/digest/off) | BE | 20 |  | 9 | Not Started | 0% | 2026-10-08 | 2026-10-08 |  |  |  | Per Charter §5.11.2.
W-099 | Phase 2 | Alerts | Escalation chains: timer-based escalate-to-admin + auto-pause on 2nd unacknowledged | BE | 16 |  | 9 | Not Started | 0% | 2026-10-08 | 2026-10-08 |  |  |  | Per Charter §5.11.3.
W-100 | Phase 2 | Alerts | Threshold-based custom alerts engine (per-adapter rule store + evaluator) | BE | 20 |  | 9 | Not Started | 0% | 2026-10-08 | 2026-10-08 |  |  |  | Volume drop, error rate, etc.
W-101 | Phase 2 | Frontend | Alerts UI: notification bell + feed + detail panel + acknowledge/escalate actions | FE | 20 |  | 9 | Not Started | 0% | 2026-10-08 | 2026-10-08 |  |  |  | Replace mock alerts.js.
W-102 | Phase 2 | Workflow | Task escalation system: Operator→Designer task with auto-attached context (mapping/error) | BE | 16 |  | 9 | Not Started | 0% | 2026-10-08 | 2026-10-08 |  |  |  | Per Charter §5.6 + §5.3.3.
W-103 | Phase 2 | Frontend | Cron builder UI in Wizard Step 5 (visual cron with next-run preview) | FE | 16 |  | 9 | Not Started | 0% | 2026-10-08 | 2026-10-08 |  |  |  | Per Charter §5.2 step 5.
W-104 | Phase 2 | Security | Resource-level RBAC overrides + admin UI to grant per-adapter permission exceptions | BE | 20 |  | 9 | Not Started | 0% | 2026-10-08 | 2026-10-08 |  |  |  | Per Charter §5.8.3.
W-105 | Phase 2 | Frontend | Audit log viewer UI in Admin (filterable by user, action, entity, date) | FE | 14 |  | 9 | Not Started | 0% | 2026-10-08 | 2026-10-08 |  |  |  | Append-only view.
W-106 | Phase 2 | Frontend | Contextual help: first-time walkthroughs + inline form hints + tooltip library | FE | 16 |  | 9 | Not Started | 0% | 2026-10-08 | 2026-10-08 |  |  |  | Per Charter §5.10.2.
W-107 | Phase 2 | QA | Alerts E2E: failure → in-app + email → escalation timer → auto-pause | QA | 16 |  | 9 | Not Started | 0% | 2026-10-08 | 2026-10-08 |  |  |  | Time-traveled tests.
W-108 | Phase 2 | QA | Phase 2 regression + security re-review (new APIs, AI sandbox boundaries) | QA | 20 |  | 9 | Not Started | 0% | 2026-10-08 | 2026-10-08 |  |  |  | Pre-UAT gate.
W-109 | Phase 2 | BA | Phase 2 UAT planning + execution + signoff | BA | 24 |  | 9 | Not Started | 0% | 2026-10-08 | 2026-10-08 |  |  |  | M9 milestone owner.
W-110 | Phase 2 | DevOps | Production deploy + monitoring (Serilog → Seq or ELK + uptime probe) | DevOps | 16 |  | 9 | Not Started | 0% | 2026-10-08 | 2026-10-08 |  |  |  | Go-live readiness.
Phase 0 subtotal
Phase 1 subtotal
Phase 2 subtotal
GRAND TOTAL
Formulas:
Days Slip = IF([Delivered Date]="","",NETWORKDAYS([Original ETA],[Delivered Date])-1)

## Milestones
Milestone ID | Milestone | Phase | Target Date | Status | Owner | Acceptance Criteria | Dependencies | Actual Date | Slip Days
M0 | Sprint 0 complete — solution scaffolded, CI green, EF migrations applied | P0 | 2026-06-05 | Not Started | Kiran | dotnet build green; dotnet test 0 failures; docker compose up healthy; CI pipeline runs in <8 min. | —
M1 | Hub engine working — first message Inbox → Channel → Router → Outbox → DLQ on forced failure | P1 | 2026-06-19 | Not Started | BE Dev | Fake source emits envelope; checksum valid; PENDING row in inbox; routes to subscription; DLQ entry on forced 500. | M0
M2 | Jira → SharePoint parity with Node version (Red Gold + Flatiron + 35-field mapper) | P1 | 2026-07-17 | Not Started | BE Dev | Live Red Gold + Flatiron pull → SP write; records-in = records-out; zero duplicates across re-run; matches Node-version output byte-for-byte for 100 sample tickets. | M1
M3 | Frontend wired end-to-end — all 13 pages on real API, mocks removed | P1 | 2026-07-31 | Not Started | FE Dev | Mock data imports removed from Dashboard/Registry/Monitor/Alerts/Vault/Connected/Push/Admin/Studio; Wizard Step 4 & 6 functional; Recharts wired. | M2
M4 | Auth + Multi-tenancy + RBAC live (4 roles + JWT + row-level org filter) | P1 | 2026-08-14 | Not Started | BE Dev | Login flow works; cross-org data isolation verified by penetration test; permission matrix per Charter §5.8.2 enforced; audit log writes on sensitive actions. | M3
M5 | MVP UAT signoff (Phase 1 complete) | P1 | 2026-08-28 | Not Started | BA | Stakeholder UAT scripts passed; Charter §10 metrics met (Operator setup <30 min, 0% hardcoded creds, test-before-publish 100%); production deploy approved. | M4
M6 | AI Auto-Map + NL Transformation GA | P2 | 2026-09-25 | Not Started | BE Dev | Auto-map >70% accuracy on 50-pair fixture (Charter §10); NL → expression sandbox compiles & runs; human-confirmation gate present. | M5
M7 | Trading Console + Health Dashboard GA (real data, real-time) | P2 | 2026-10-09 | Not Started | FE Dev | Per-message trace expandable; one-click Create Task; Charts/SVG removed; 4-worker Parallel mode demonstrates 3x throughput vs Serial. | M6
M8 | Master Entity Catalog + DB/File/MQ connectors + Scraping Engine GA | P2 | 2026-10-30 | Not Started | BE Dev | Entity tree + field-level usage live; SQL Server + Postgres + CSV + Apify + Playwright connectors pass happy + error paths; scraping-breakage screenshot alert wired. | M7
M9 | Phase 2 UAT signoff + production deploy | P2 | 2026-11-13 | Not Started | BA | Full Phase 2 acceptance script passed; alerting end-to-end (email + escalation + auto-pause); RBAC resource overrides verified; on-call runbook handed over. | M8
Formulas:
Slip Days = IF([Actual Date]="","",NETWORKDAYS([Target Date],[Actual Date])-1)

## Effort Summary
Effort by Phase × Role (live from WBS — never edit cells here)
Phase | BA Hours | FE Dev Hours | BE Dev Hours | QA Hours | DevOps Hours | Total Vibe Hours | Total Person-Days | % of Total
Phase 0
Phase 1
Phase 2
GRAND TOTAL | [7 empty] | 100.0%
Capacity check — over-allocation flag
Role | Total Vibe Hours | Person-Days | Months (÷160) | Calendar Months Avail | Capacity Flag
BA |  |  |  | 5.6
FE |  |  |  | 5.6
BE |  |  |  | 5.6
QA |  |  |  | 5.6
DevOps |  |  |  | 5.6
Note: BE Dev Hours sums both 'BE' and 'Backend' role tags on WBS. Adjust headcount if any role is OVER-ALLOCATED.

## Sprint Plan
Sprint | Start Date | End Date | Sprint Goal | Demo Items | Capacity Hours | Loaded Hours | Utilization % | Milestone Hit
Sprint 0 | 2026-05-25 | 2026-06-05 | Sprint 0 — Foundation & Setup | .NET solution skeleton · EF Core schema · docker-compose · CI green · BA baseline doc · QA test strategy | 320 |  |  | M0
Sprint 1 | 2026-06-08 | 2026-06-19 | Sprint 1 — Hub Core Abstractions + Persistence | ISourceConnector/IDest/ITransform interfaces · MessageEnvelope · IntegrationBus + Channels · 4 repositories | 320 |  |  | —
Sprint 2 | 2026-06-22 | 2026-07-03 | Sprint 2 — Router, Workers, Transform, Polly, DLQ | Router fan-out · SubscriptionWorker · TransformPipeline · Polly retry + breaker · DLQ auto-replay | 320 |  |  | M1
Sprint 3 | 2026-07-06 | 2026-07-17 | Sprint 3 — Port Jira (Red Gold + Flatiron) + SharePoint + Mapper | Live Jira→SP via .NET; parity to Node baseline on 100-ticket fixture | 320 |  |  | M2
Sprint 4 | 2026-07-20 | 2026-07-31 | Sprint 4 — Vault, Scheduler, Run mgmt, API parity, RBAC schema | Quartz cron · CredentialService AES-256 · /integrations + /jira + /sp routes · JWT + RLS · audit middleware | 320 |  |  | —
Sprint 5 | 2026-08-03 | 2026-08-14 | Sprint 5 — Frontend wire-up + Studio backend + MVP UAT | 13 pages wired (no mocks) · Login · Wizard 4+6 · Studio · Recharts · UAT signoff | 320 |  |  | M3, M4, M5
Sprint 6 | 2026-08-17 | 2026-08-28 | Sprint 6 — AI Auto-Mapping + NL Transformation | Claude-API mapper with >70% accuracy · NL→Roslyn sandbox · Canvas auto-map UX | 320 |  |  | M6
Sprint 7 | 2026-08-31 | 2026-09-11 | Sprint 7 — Trading Console + Health Dashboard (real-time) | Per-message trace · adapter tiles + volume + error trend · 4-worker perf demo | 320 |  |  | M7
Sprint 8 | 2026-09-14 | 2026-09-25 | Sprint 8 — Master Entity Catalog + DB/File/MQ + Scraping | Entity tree + 5 new connectors (SQL/PG/CSV/Apify/Playwright) | 320 |  |  | M8
Sprint 9 | 2026-09-28 | 2026-10-09 | Sprint 9 — Full Alerting + Task Escalation + RBAC overrides + Phase 2 UAT | Email alerts + escalation + auto-pause · cron UI · resource overrides · audit viewer · prod deploy | 320 |  |  | M9
Capacity assumption: 4 people × 8 hrs × 10 working days = 320 hrs/sprint. Adjust col F if team size changes.

## Risks & Open Items
ID | Type | Description | Probability | Impact | Severity | Mitigation / Action | Owner | Due Date | Status
R-01 | Risk | External API access not obtainable for some target systems (auth, rate limits, IP allow-list) | M | H |  | Three-tier fallback: browser-passthrough auth → Apify cloud → Playwright self-hosted. Flag scraping connectors with bot icon in registry. | BA | 2026-06-15 | Open
R-02 | Risk | Web scraping connectors break when target UI changes | H | M |  | Screenshot-diff alert on scrape failure; Designer notified immediately; flag scraping connectors as high-maintenance. | BE Dev | 2026-09-01 | Open
R-03 | Risk | Scope creep — Charter Phase 3/4 items pulled into MVP | H | H |  | Lock scope per phase; change-request process; weekly scope review against Charter §8 phase boundaries. | BA | 2026-05-29 | Open
R-04 | Risk | AI field mapper produces poor suggestions in domain-specific schemas | M | M |  | Always require human confirmation; log confirm/reject decisions to tune prompt; graceful fallback to manual map. | BE Dev | 2026-09-18 | Open
R-05 | Risk | Non-technical Operators find Mapping Canvas too complex | M | H |  | Two rounds of moderated UX testing in Sprint 5 + 8; progressive disclosure; one-click Request Designer Help. | BA | 2026-08-15 | Open
R-06 | Risk | Credential vault security vulnerability | L | C |  | AES-256-GCM + security review (M5 gate); never log raw values; OWASP top-10 covered in Sprint 5 QA task. | BE Dev | 2026-08-28 | Open
R-07 | Risk | Node→.NET port effort underestimated (Playwright/Flatiron MFA esp.) | M | H |  | Validate with thin Sprint 1 slice; rebaseline B1 vibe multiplier and Trad Hours if Sprint 3 spillover >20%. | Kiran | 2026-07-17 | Open
R-08 | Risk | Microsoft.Playwright (.NET) reliability for long-running MFA sessions | M | M |  | Run 24-hour headless soak in Sprint 3; keep storageState persistence + re-login fallback identical to Node version. | BE Dev | 2026-07-17 | Open
R-09 | Risk | 0.5x Vibecoding multiplier may not hold for complex hub logic (channels, Polly, RLS) | M | H |  | Track actual vs. Vibe Hours per task; review at end of Sprint 2; rebaseline B1 cell if variance >25%. | Kiran | 2026-06-19 | Open
R-10 | Risk | Frontend mock-to-real swap surfaces hidden contract gaps (shape mismatch, missing fields) | M | M |  | Generate TypeScript types from .NET DTOs (NSwag) before FE wire-up; contract tests in Sprint 4 (W-060). | FE Dev | 2026-07-24 | Open
R-11 | Risk | OAuth2/MFA flows for SharePoint + Flatiron sensitive to client config drift | M | H |  | Per-client smoke job after deploy; alert on auth-error spike; document tenant prerequisites in onboarding doc. | BE Dev | 2026-08-14 | Open
D-01 | Decision | Final backend choice — .NET 8 vs Python (FastAPI) | — | H |  | Default .NET (matches all design docs). Re-affirm at Sprint 0 close; if changed, swap BE tasks to Python equivalents (FastAPI + SQLAlchemy + Celery + Playwright-Python). | Kiran | 2026-06-05 | Open
D-02 | Decision | AI provider for auto-mapping — Claude API / OpenAI / local model | — | M |  | Bench-test top 2 candidates on a 50-pair fixture in Sprint 5; pick on cost × accuracy × latency. | BE Dev | 2026-09-04 | Open
D-03 | Decision | Hosting model — local / Docker / cloud (Azure or AWS) | — | M |  | Start local + Docker; choose cloud target by Sprint 2 to inform DevOps work in Sprint 4-5. | DevOps | 2026-06-19 | Open
D-04 | Decision | First two production clients/connectors after MVP | — | M |  | Confirm with stakeholders by Sprint 1 demo. Drives Phase 2 connector priority (DB/File/MQ vs scraping). | BA | 2026-06-19 | Open
D-05 | Decision | Transformation scripting language — Roslyn C# / Python / JavaScript / DSL | — | M |  | Default Roslyn C# (matches .NET host). Revisit if Python backend chosen (use RestrictedPython). | BE Dev | 2026-08-28 | Open