## 1. Cover & Read-Me
SYNAPSE INTEGRATION PLATFORM — PROJECT PLAN
Day-level WBS for Phase 2 → Phase 4 ¦ Companion to Synapse_BRD_v1.docx
| Version | 1.0
| Date | 2026-05-04
| Owner | Synapse Product Team
| Classification | Internal
| BU | Nalashaa Digital (GLOBAL)
| Companion BRD | Synapse_BRD_v1.docx
| Companion Charter | Synapse_Product_Charter_v2.pdf
Capacity Assumption
• 1 full-time developer + Claude Code (vibe coding).
• Working hours: 6–8 productive coding hours per day (pair-programming with AI).
• Aggressive day-level estimates throughout — phases may compress further with strong session continuity.
• Estimates exclude calendar holidays; absorb interruptions in a 10% buffer per phase.
Tab Guide
| 1. Cover & Read-Me | This tab. Capacity, conventions, status legend, glossary.
| 2. Current State Snapshot | Module status today (Built / Partial / Stub / Missing) — one-page picture.
| 3. WBS | Master backlog: every story with phase, module, epic, estimate, dependencies, status.
| 4. Phase 2 Day Plan | Days 1 → ~40. Goal of the day, files touched, test that proves done.
| 5. Phase 3 Day Plan | Days ~41 → ~70. Scale & Governance items.
| 6. Phase 4 Day Plan | Days ~71 → ~90. Polish & Distribution.
| 7. Milestones | Demo and go-live checkpoints.
| 8. Gantt | Visual timeline — bars per epic across the day axis.
| 9. Risks | Risk register with likelihood, impact, mitigation, owner.
| 10. Open Decisions | Open product / engineering decisions with decide-by day numbers.
Status Legend
| Not Started | Editable status — drives conditional formatting throughout the workbook.
| In Progress | Editable status — drives conditional formatting throughout the workbook.
| Blocked | Editable status — drives conditional formatting throughout the workbook.
| Done | Editable status — drives conditional formatting throughout the workbook.
Cell Color Key
| Editable | Update as you progress (Status, Notes, Actual Days)
| Calculated | Formula-driven — do not edit
| Header | Tab header — locked
© 2026 Nalashaa Solutions India Pvt. Ltd. ¦ Confidential — Internal Use Only

## 2. Current State Snapshot
Current State Snapshot — As of 4 May 2026
Source: codebase walkthrough + PRODUCT_STATUS.md
# | Module | Status | Notes
1 | Jira Source — REST API (Red Gold) | Built | Basic Auth + JQL search, retries, custom-field parsing, normaliser.
2 | Jira Source — Browser Automation (Flatiron) | Built | Playwright SSO/MFA, TOTP, 8h cookie session cache.
3 | SharePoint Destination | Built | OAuth2 client credentials, Graph API site/list resolution, batched 20/req.
4 | Field Mapping (Jira → SharePoint, 35 fields) | Built | 12 standard + 23 derived (CycleTimeDays, IsOverdue, SprintNumber, etc.).
5 | Credential Encryption (AES-256-GCM) | Built | Store-only; no GET/decrypt endpoint yet.
6 | Integration CRUD | Built | Zod-validated, JSONB mappings + retry policy.
7 | Run Tracking | Built | Status pending → running → success/error, record counts.
8 | Cron Scheduling (BullMQ repeatable) | Built | PATCH /connected/:id/schedule.
9 | Delta Sync (3 modes) | Built | RESYNC, EXTEND_TO_TODAY, CUSTOM. Watermark-based.
10 | 3-Layer Dedup | Built | pushLog → jiraItemCache → SharePoint live query.
11 | Connection Wizard (6-step) | Partial | Only Step 2 (Test Connection) wired. Steps 1, 3, 4, 5, 6 use mock data.
12 | Mapping Canvas | Partial | Pure-frontend with simulated AI auto-map. Not persisted.
13 | Push Page | Partial | Form-based; talks to /api/sharepoint/push.
14 | Connector Studio | Stub | Test/Publish buttons disabled (StudioPage.jsx:86). No backend.
15 | Health Dashboard | Stub UI | Beautiful UI, all mock data.
16 | Integration Registry | Stub UI | Cards + sparklines; mock integrations.js.
17 | Trading Network Console (Monitor) | Stub UI | Mock monitorData.js.
18 | Alerts Page | Stub UI | Mock alerts.js. No backend dispatch.
19 | Credential Vault Page | Stub UI | Mock credentials.js. Eye-icon UX present.
20 | Master Entity Catalog | Stub UI | Tree + field usage on hardcoded data.
21 | Connected (Integrations Dashboard) | Stub UI | Mock data; schedule modal works against real backend in some paths.
22 | Admin (Users + Client Apps) | Stub UI | Mock data; no auth backend.
23 | User Auth + JWT | Missing | users + role enum + organizations exist; never enforced.
24 | RBAC Enforcement | Missing | No middleware checks role on routes.
25 | Multi-Tenancy | Missing | Hardcoded org UUID.
26 | Alerts System (creation + dispatch) | Missing | DB table + queue declared; no logic.
27 | Audit Log Writer | Missing | DB table exists; nothing writes to it.
28 | Web Scraping (Apify / Playwright actor) | Missing | Charter Phase 2.
29 | DB / File Share / MQ Connector Types | Missing | Charter Phase 2.
30 | AI Auto-Mapping (real LLM) | Missing | Stub UI only.
31 | AI Help Assistant | Missing | Charter Phase 3.
32 | Dynamics 365 / TARA / PostgreSQL / Excel / Keka connectors | Missing | Phase 2 expansion.
33 | TFS / Holiday Tracker / Ahrefs / GSC / Google Adwords destinations | Missing | Phase 2-3 expansion.
Tally
Built
Partial
Stub UI
Stub
Missing

## 3. WBS
Work Breakdown Structure
Master backlog. Estimates in working days for 1 developer + Claude. Status drives conditional formatting.
ID | Phase | Module | Epic | Story | Acceptance Criteria (summary) | Est (d) | Dependencies | Risk | Status
F-01 | P2 | Foundation | Auth & RBAC | JWT login + auth middleware | Login screen issues JWT; middleware decodes user + role; protected routes return 401 without token. | 3 | — | Med | Not Started
F-02 | P2 | Foundation | Auth & RBAC | User CRUD + role assignment | Admin can create/list/update/deactivate users; role enum enforced server-side. | 2 | F-01 | Low | Not Started
F-03 | P2 | Foundation | Auth & RBAC | Role-based route guards | withRole(['admin','designer']) decorator on every state-changing route; tests cover 401/403. | 2 | F-01 | Low | Not Started
F-04 | P2 | Foundation | Wiring | Wire Dashboard page to real API | Dashboard summary endpoint returns counts + sparkline data; mock removed. | 1 | F-01 | Low | Not Started
F-05 | P2 | Foundation | Wiring | Wire Registry page to real API | GET /api/integrations populates cards; sparklines call /api/runs?since=7d. | 1 | F-04 | Low | Not Started
F-06 | P2 | Foundation | Wiring | Wire Connected page | GET /api/connected returns groups + schedules; ConnectedPage replaces inline mock. | 1 | F-05 | Low | Not Started
F-07 | P2 | Foundation | Wiring | Wire Vault page | GET /api/credentials returns metadata + mask; reveal calls /api/credentials/:id with audit log. | 1 | F-09 | Low | Not Started
F-08 | P2 | Foundation | Wiring | Wire Admin page | Users + Client Apps tabs read /api/users + /api/clients; RBAC respected. | 1 | F-02 | Low | Not Started
F-09 | P2 | Foundation | Vault | Credential GET + decrypt + audit | GET /api/credentials/:id decrypts and returns; reveal logged with user + IP. | 1 | F-01 | Low | Not Started
F-10 | P2 | Foundation | Charts | Add Recharts and standard chart components | Recharts installed; Sparkline, BarChart, LineChart components built once and reused. | 1 | — | Low | Not Started
CS-01 | P2 | Connector Studio | Backend | Connector CRUD endpoints | POST/GET/PATCH/DELETE /api/connectors with versioning. app.connectors becomes active. | 2 | F-03 | Med | Not Started
CS-02 | P2 | Connector Studio | Backend | OpenAPI parser | Upload Swagger/OpenAPI 3.0; backend returns endpoints + schemas. | 2 | CS-01 | Med | Not Started
CS-03 | P2 | Connector Studio | Backend | Database schema introspection | Connection string → list of tables with column types via Drizzle Kit introspect. | 2 | CS-01 | Med | Not Started
CS-04 | P2 | Connector Studio | Backend | Connector test + publish | POST /test runs sample call; POST /publish gated on success; new version created. | 1 | CS-02 | Low | Not Started
CS-05 | P2 | Connector Studio | Frontend | Studio UI wire-up | Test Connection + Publish buttons enabled. Form posts to /api/connectors. Versions visible. | 2 | CS-04 | Low | Not Started
CS-06 | P2 | Connector Studio | Frontend | Entity modeller drag-drop | Group raw fields into entities; rename labels; persist entity_definitions. | 2 | CS-05 | Med | Not Started
M-01 | P2 | Mapping Engine | AI | AI Auto-Map service (Claude API) | POST /api/integrations/:id/mappings/auto-map returns suggestions + confidence ≥70% on test set. | 3 | F-10 | Med | Not Started
M-02 | P2 | Mapping Engine | AI | NL transformation generator | Operator types 'convert ISO date to dd/mm/yyyy'; backend returns JS function. | 2 | M-01 | Med | Not Started
M-03 | P2 | Mapping Engine | Backend | JS sandbox (QuickJS) for transforms | Transformations run in sandbox; CPU + memory limits; no host access. | 2 | M-02 | High | Not Started
M-04 | P2 | Mapping Engine | Frontend | Canvas wire-up to real API | AI Auto-Map button calls real endpoint; lines colour-state machine; mappings persist. | 2 | M-01 | Low | Not Started
M-05 | P2 | Mapping Engine | Frontend | Mapping validation UI | Validate button checks types + required + cycles; checklist with pass/fail. | 1 | M-04 | Low | Not Started
MN-01 | P2 | Monitoring | Backend | Activate run_messages writes | Every push/pull writes a row to run_messages; payload hash + status. | 1 | F-03 | Low | Not Started
MN-02 | P2 | Monitoring | Backend | Real-time stream endpoint | GET /api/messages/stream (SSE) or polling; Trading Console subscribes. | 1 | MN-01 | Med | Not Started
MN-03 | P2 | Monitoring | Frontend | Trading Network Console wire-up | Live table; expandable rows show payload + mapping trace; pause button freezes view. | 2 | MN-02 | Low | Not Started
MN-04 | P2 | Monitoring | Backend | Health Dashboard summary endpoints | GET /api/dashboard/{summary,volume,errors-trend,client-tiers}; <500ms via materialised views. | 2 | F-03 | Med | Not Started
MN-05 | P2 | Monitoring | Frontend | Health Dashboard charts wire-up | DashboardPage uses Recharts components; KPI tiles + volume + trend. | 1 | MN-04, F-10 | Low | Not Started
AL-01 | P2 | Alerts | Backend | AlertService.create() + DB writes | Failure paths in workers call AlertService; app.alerts populated. | 1 | F-03 | Low | Not Started
AL-02 | P2 | Alerts | Backend | alert-dispatcher worker | Worker reads queue; routes to in-app + email per rule. | 1 | AL-01 | Low | Not Started
AL-03 | P2 | Alerts | Backend | Email transport (nodemailer + SMTP) | SMTP env config; immediate critical, daily digest warnings. | 1 | AL-02 | Low | Not Started
AL-04 | P2 | Alerts | Frontend | AlertsPage wire-up | GET /api/alerts; acknowledge/escalate buttons hit real endpoints. | 1 | AL-01 | Low | Not Started
AL-05 | P2 | Alerts | Backend | Threshold-based alerts | Per-adapter or global thresholds; cron evaluates daily. | 1 | AL-04 | Low | Not Started
MC-01 | P2 | Master Catalog | Backend | entities + entity_fields tables + repo | New tables, repository pattern, backfill from existing fieldMappings. | 1 | F-03 | Low | Not Started
MC-02 | P2 | Master Catalog | Backend | Entity tree + usage endpoints | GET /api/entities returns tree; GET /api/entities/:id/usage returns adapter list. | 1 | MC-01 | Low | Not Started
MC-03 | P2 | Master Catalog | Frontend | CatalogPage wire-up | Tree navigation; field usage bars; cross-reference links work. | 2 | MC-02 | Low | Not Started
HS-01 | P2 | Help System | Backend | Markdown content + lunr.js index | /help/*.md authored; build-time index generated. | 2 | — | Low | Not Started
HS-02 | P2 | Help System | Frontend | HelpPanel wire-up + search | '?' icon opens panel pre-filtered to current screen; search works. | 1 | HS-01 | Low | Not Started
HS-03 | P2 | Help System | Frontend | Tooltips + first-time walkthroughs | shepherd.js walkthrough on first visit per major screen; tooltips on icons. | 2 | HS-02 | Low | Not Started
NS-01 | P2 | New Sources | Connector | PostgreSQL source connector | Schema introspection + parametrised SELECT query; entity output matches Jira format. | 2 | CS-03 | Med | Not Started
NS-02 | P2 | New Sources | Connector | Excel/CSV source connector | Upload or SFTP/SharePoint location; sheet/range selection; type inference. | 1 | CS-01 | Low | Not Started
NS-03 | P2 | New Sources | Connector | Dynamics 365 source connector | OData/Web API + Azure AD OAuth2; entity discovery. | 3 | CS-02 | Med | Not Started
NS-04 | P2 | New Sources | Connector | Keka source connector | REST API + API Key; employee/leave entity templates. | 2 | CS-02 | Low | Not Started
NS-05 | P2 | New Sources | Connector | TARA source connector | REST API or scraping fallback; project/test entity templates. | 2 | CS-02 | Med | Not Started
ND-01 | P2 | New Destinations | Connector | TFS / Azure DevOps destination | REST API + PAT/OAuth; create work items; mapping template for Jira issues. | 3 | CS-02 | Med | Not Started
ND-02 | P2 | New Destinations | Connector | Holiday Tracker destination | REST API or DB write per implementation discovery. | 1 | CS-01 | Low | Not Started
WS-01 | P2 | Web Scraping | Backend | Apify cloud actor wrapper | Configure target URL + selectors; schedule jobs; retrieve dataset. | 2 | CS-01 | Med | Not Started
WS-02 | P2 | Web Scraping | Backend | Playwright self-hosted actor | Recorded flow runs; structured JSON output; screenshot on failure. | 3 | CS-01 | Med | Not Started
SG-01 | P3 | Scale & Governance | Client Apps | Client App registration + token lifecycle | External app registers; client_id/secret issued; refresh + revocation. | 2 | F-01 | Med | Not Started
SG-02 | P3 | Scale & Governance | Master Catalog | Entity merge with impact analysis | Side-by-side diff; preview affected adapters; post-merge re-test flag. | 3 | MC-03 | High | Not Started
SG-03 | P3 | Scale & Governance | Master Catalog | Entity evolution / cascade | Field add/rename shows downstream impact; preview-before-commit. | 2 | SG-02 | Med | Not Started
SG-04 | P3 | Scale & Governance | AI Ops | Self-healing diagnoses | AI proposes fixes for common failure patterns; dry-run before apply. | 4 | M-01 | High | Not Started
SG-05 | P3 | Scale & Governance | Webhooks | Webhook support (in/out) | Inbound webhook handler with HMAC signing; outbound webhook adapter type. | 2 | F-03 | Med | Not Started
SG-06 | P3 | Scale & Governance | Operations | Bulk operations | Multi-select pause/resume; batch re-test after entity change. | 2 | F-05 | Low | Not Started
SG-07 | P3 | Scale & Governance | Audit | Audit middleware writes + UI | Every state-changing route writes to audit_log; timeline UI filterable by user/entity/action. | 2 | F-03 | Low | Not Started
SG-08 | P3 | Scale & Governance | RBAC | Resource-level permission overrides | Per-adapter Designer access for an Operator; UI to grant + revoke. | 2 | F-03 | Med | Not Started
SG-09 | P3 | Scale & Governance | Help System | AI Help Assistant | Conversational chatbot with screen state + recent actions context. | 4 | HS-02, M-01 | Med | Not Started
SG-10 | P3 | Scale & Governance | Connectors | Ahrefs destination | REST API + token; rank tracking entity templates. | 2 | CS-02 | Low | Not Started
SG-11 | P3 | Scale & Governance | Connectors | Google Search Console destination | Service Account / OAuth; performance/coverage entities. | 2 | CS-02 | Low | Not Started
SG-12 | P3 | Scale & Governance | Connectors | Google Adwords destination | Google Ads API + OAuth2 + dev token; campaign/ad-group entities. | 3 | CS-02 | Med | Not Started
P4-01 | P4 | Polish | Theming | Theme engine (light/dark + custom logo) | User toggles theme; per-org logo upload. | 1 | — | Low | Not Started
P4-02 | P4 | Polish | Mobile | Mobile-responsive PWA | Service worker, manifest, responsive break-points; monitor pages usable on tablet. | 3 | — | Med | Not Started
P4-03 | P4 | Polish | Onboarding | First-time user onboarding wizard | 5-step welcome flow for first login; skippable. | 2 | F-01 | Low | Not Started
P4-04 | P4 | Polish | Packaging | Docker image + one-command deploy | Single docker compose pulls image + DB + Redis; .env template. | 2 | — | Low | Not Started
P4-05 | P4 | Polish | Docs | Architecture guide | ADRs for auth, RBAC, scraping, AI mapping, encryption. | 1 | — | Low | Not Started
P4-06 | P4 | Polish | Docs | User manual (per persona) | Designer / Operator / Admin guides with screenshots. | 2 | HS-01 | Low | Not Started
P4-07 | P4 | Polish | Docs | API reference | OpenAPI YAML auto-generated from routes; published as docs site. | 1 | — | Low | Not Started
P4-08 | P4 | Polish | Docs | Handover package | Bundled archive: BRD + plan + README + CLAUDE.md + runbook. | 1 | P4-05, P4-06, P4-07 | Low | Not Started
P4-09 | P4 | Polish | QA | Final QA pass + Playwright e2e suite | End-to-end test per page; CI-friendly; runs <10 min. | 3 | all P2/P3 | Med | Not Started
Phase Totals
Phase | Items | Estimate (d) | Done | Done %
Phase 2
Phase 3
Phase 4
GRAND TOTAL

## 4. Phase 2 Day Plan
Phase 2 — Intelligence & Monitoring + Multi-Source
Days 1 → 66. Capacity: 1 dev + Claude. Aggressive vibe-coded pace.
Day # | Calendar Date | Story ID | Goal of the Day | Files Touched | Test That Proves Done | Status
1 | 2026-05-05 | F-01 | JWT login + auth middleware (backend) | auth.routes.ts, jwtMiddleware.ts, login.tsx | 401 on protected route without token; 200 with valid JWT. | Not Started
2 | 2026-05-06 | F-01 | Login page UI + token storage (frontend) | components/auth/LoginPage.jsx, services/auth.js | Login form posts to /api/auth/login, stores JWT, redirects. | Not Started
3 | 2026-05-07 | F-02 | User CRUD endpoints + role assignment | api/users.routes.ts, db/repositories/userRepo.ts | Admin creates user; role enum enforced; tests cover all 4 roles. | Not Started
4 | 2026-05-08 | F-03 | Role-based route guards everywhere | middleware/withRole.ts, all routes | Admin-only route returns 403 for Operator; tests added per route. | Not Started
5 | 2026-05-09 | F-08 | Admin page wire-up (Users tab + Client Apps tab) | components/admin/AdminPage.jsx, services/api.js | AdminPage shows real users; role edit modal saves to backend. | Not Started
6 | 2026-05-10 | F-10 | Recharts install + Sparkline/BarChart/LineChart components | components/shared/charts/*.jsx, package.json | Storybook-style demo page renders all 3 chart types. | Not Started
7 | 2026-05-11 | F-04 | Wire Dashboard page to real summary endpoint | components/dashboard/DashboardPage.jsx, api/dashboard.routes.ts | KPI tiles show real counts; backend returns <500ms. | Not Started
8 | 2026-05-12 | F-05 | Wire Registry + sparklines | components/registry/RegistryPage.jsx | Cards populated from /api/integrations; sparklines plot last 7 days runs. | Not Started
9 | 2026-05-13 | F-06 | Wire Connected page (groupings + schedules) | components/connected/ConnectedPage.jsx | Cards grouped by client; schedule modal saves cron. | Not Started
10 | 2026-05-14 | F-09 | Credential GET + decrypt + audit reveal | api/credentials.routes.ts, services/CredentialService.ts | GET /api/credentials/:id decrypts; reveal logged in audit_log. | Not Started
11 | 2026-05-15 | F-07 | Wire Vault page (mask/reveal) | components/vault/VaultPage.jsx | List populates from /api/credentials; reveal calls real endpoint with timer. | Not Started
12 | 2026-05-16 | CS-01 | Connector backend CRUD + versioning (part 1) | api/connectors.routes.ts, db/schema.ts (connector_versions) | POST/GET /api/connectors works; new version on update. | Not Started
13 | 2026-05-17 | CS-01 | Connector backend CRUD (part 2) + tests | api/connectors.routes.ts, __tests__/connectors.test.ts | Vitest suite green; RBAC enforces designer-only writes. | Not Started
14 | 2026-05-18 | CS-02 | OpenAPI parser service | services/OpenAPIParser.ts | Upload OpenAPI 3.0 → returns endpoints + schemas. | Not Started
15 | 2026-05-19 | CS-02 | Operation discovery + filtering UI | components/studio/OperationDiscovery.jsx | Designer ticks operations to expose; tags Read/Write/Both. | Not Started
16 | 2026-05-20 | CS-03 | Database schema introspection | services/DBIntrospector.ts | Postgres connection string → table list with column types. | Not Started
17 | 2026-05-21 | CS-04 | Connector test + publish endpoints | api/connectors.routes.ts (publish), services/ConnectorTester.ts | Publish gated on successful test; version increments. | Not Started
18 | 2026-05-22 | CS-05 | Studio UI wire-up (enable Test/Publish buttons) | components/studio/StudioPage.jsx | StudioPage.jsx:86 buttons enabled; round-trip works. | Not Started
19 | 2026-05-23 | CS-06 | Entity modeller drag-drop (part 1) | components/studio/EntityModeller.jsx | Designer groups raw fields into entities; labels editable. | Not Started
20 | 2026-05-24 | CS-06 | Entity modeller (part 2) + persist entity_definitions | db/schema.ts (entity_definitions), components/studio/EntityModeller.jsx | Save persists; reload restores layout. | Not Started
21 | 2026-05-25 | MC-01 | Master Catalog tables + repo | db/schema.ts (entities, entity_fields), db/repositories/entityRepo.ts | Tables created via Drizzle migration; repo CRUD tested. | Not Started
22 | 2026-05-26 | MC-02 | Entity tree + usage endpoints | api/entities.routes.ts | GET /api/entities returns tree; usage count joins integrations.fieldMappings. | Not Started
23 | 2026-05-27 | MC-03 | CatalogPage wire-up (part 1) — tree nav | components/catalog/CatalogPage.jsx | Tree from real API; clicking entity loads fields panel. | Not Started
24 | 2026-05-28 | MC-03 | CatalogPage (part 2) — field usage bars + cross-ref | components/catalog/CatalogPage.jsx, components/shared/charts/UsageBar.jsx | Field usage statistics displayed; click to see adapters. | Not Started
25 | 2026-05-29 | M-01 | Anthropic SDK + AI Auto-Map service (part 1) | services/MappingAIService.ts, package.json | POST /api/integrations/:id/mappings/auto-map returns suggestions. | Not Started
26 | 2026-05-30 | M-01 | AI Auto-Map (part 2) — confidence scoring + tests | services/MappingAIService.ts, __tests__/mappingAI.test.ts | Test set hits ≥70% accuracy on known Jira→SP mappings. | Not Started
27 | 2026-05-31 | M-01 | AI Auto-Map (part 3) — caching + cost guardrails | services/MappingAIService.ts (cache layer) | Repeated identical request hits cache; daily cost cap enforced. | Not Started
28 | 2026-06-01 | M-02 | NL transformation generator | services/NLTransformService.ts, api/integrations.routes.ts | Operator NL input → JS function returned; sample tests pass. | Not Started
29 | 2026-06-02 | M-03 | QuickJS sandbox (part 1) — runtime + limits | services/SandboxService.ts, package.json | Sandbox spawns; CPU/memory limits enforced; no host fs access. | Not Started
30 | 2026-06-03 | M-03 | QuickJS sandbox (part 2) — wire into push pipeline | services/SharePointPushService.ts (transformations) | Transformations applied per mapping line during real push. | Not Started
31 | 2026-06-04 | M-04 | Canvas wire-up to real AI + persistence | components/canvas/CanvasPage.jsx, services/api.js | AI Auto-Map button calls real endpoint; mapping saves to integrations.fieldMappings. | Not Started
32 | 2026-06-05 | M-05 | Mapping validation UI + checklist | components/canvas/CanvasPage.jsx (validate panel) | Validate button: types compatible, required mapped, no cycles. | Not Started
33 | 2026-06-06 | MN-01 | Activate run_messages writes | workers/syncWorker.ts, services/SharePointPushService.ts | Each push/pull writes a row; payload hash stored. | Not Started
34 | 2026-06-07 | MN-02 | Real-time stream endpoint (SSE) | api/messages.routes.ts (stream) | SSE feed sends new rows in <1s; client reconnects on drop. | Not Started
35 | 2026-06-08 | MN-03 | Trading Network Console wire-up | components/monitor/MonitorPage.jsx | Live table + expand rows + payload + mapping trace + pause. | Not Started
36 | 2026-06-09 | MN-04 | Health Dashboard summary endpoints | api/dashboard.routes.ts, db/views.sql (materialised) | All 4 endpoints return <500ms. | Not Started
37 | 2026-06-10 | MN-05 | Health Dashboard charts wire-up | components/dashboard/DashboardPage.jsx | Volume bar + trend line + client tier ribbon all live. | Not Started
38 | 2026-06-11 | AL-01 | AlertService.create() + DB writes from worker failure paths | services/AlertService.ts, workers/integrationRunner.ts | Failing run inserts alert row with severity + integration ref. | Not Started
39 | 2026-06-12 | AL-02 | alert-dispatcher worker logic | workers/alertDispatcher.ts | Worker reads queue; routes to in-app + email per user prefs. | Not Started
40 | 2026-06-13 | AL-03 | Email transport (nodemailer + SMTP) | services/EmailService.ts, .env | Critical alert delivers email; daily digest job scheduled. | Not Started
41 | 2026-06-14 | AL-04 | AlertsPage wire-up + acknowledge/escalate | components/alerts/AlertsPage.jsx | Acknowledge button calls real API; alert moves to acknowledged state. | Not Started
42 | 2026-06-15 | AL-05 | Threshold-based custom alerts | services/ThresholdService.ts, daily cron job | Threshold breach generates alert; admin UI to configure. | Not Started
43 | 2026-06-16 | HS-01 | Help content authoring + lunr index (part 1) | docs/help/*.md, scripts/build-help-index.js | 10+ articles authored; index built at build time. | Not Started
44 | 2026-06-17 | HS-01 | Help content (part 2) — per-persona guides + screenshots | docs/help/*.md, public/help/screenshots/* | Designer/Operator/Admin guides complete; screenshots embedded. | Not Started
45 | 2026-06-18 | HS-02 | HelpPanel wire-up + search | components/layout/HelpPanel.jsx | '?' icon opens panel; search returns ranked results. | Not Started
46 | 2026-06-19 | HS-03 | Tooltips + first-time walkthroughs | components/shared/Tooltip.jsx, walkthroughs/*.js (shepherd.js) | Tooltip on every icon; walkthrough on first visit per major screen. | Not Started
47 | 2026-06-20 | HS-03 | Walkthrough polish + dismissable + re-accessible | components/layout/HelpMenu.jsx | User can re-launch walkthrough from Help menu. | Not Started
48 | 2026-06-21 | NS-01 | PostgreSQL source connector | integrations/postgres/*, services/PostgresExtractor.ts | Schema introspect + parametrised SELECT; entities match Jira format. | Not Started
49 | 2026-06-22 | NS-01 | PostgreSQL pagination + delta sync support | services/PostgresExtractor.ts (cursor-based) | Large tables paginate; delta query via timestamp watermark. | Not Started
50 | 2026-06-23 | NS-02 | Excel/CSV source connector | integrations/excel/*, services/ExcelParser.ts | Upload XLSX or read from SharePoint path; sheet/range selection. | Not Started
51 | 2026-06-24 | NS-03 | Dynamics 365 source connector (part 1) — auth + discovery | integrations/dynamics/*, services/DynamicsClient.ts | Azure AD OAuth2; entity discovery via OData $metadata. | Not Started
52 | 2026-06-25 | NS-03 | Dynamics 365 (part 2) — entity templates | integrations/dynamics/templates/* | Account/Contact/Lead templates with default field labels. | Not Started
53 | 2026-06-26 | NS-03 | Dynamics 365 (part 3) — testing + delta sync | integrations/dynamics/*, __tests__/dynamics.test.ts | Delta sync via modifiedon timestamp; test against sandbox. | Not Started
54 | 2026-06-27 | NS-04 | Keka source connector (part 1) | integrations/keka/* | REST API + API Key; employee/leave templates. | Not Started
55 | 2026-06-28 | NS-04 | Keka source connector (part 2) — testing + docs | integrations/keka/*, docs/help/keka-connector.md | Sandbox tested; help article published. | Not Started
56 | 2026-06-29 | NS-05 | TARA source connector (part 1) | integrations/tara/* | REST API or scraping fallback discovered; project/test entities. | Not Started
57 | 2026-06-30 | NS-05 | TARA source connector (part 2) — finalize | integrations/tara/* | Templates + tests; help article. | Not Started
58 | 2026-07-01 | ND-01 | TFS / Azure DevOps destination (part 1) | integrations/tfs/*, services/TFSPushService.ts | REST API + PAT; create work items in dev project. | Not Started
59 | 2026-07-02 | ND-01 | TFS (part 2) — mapping template + dedup | integrations/tfs/templates/* | Jira issue → Work Item mapping template; dedup on Title. | Not Started
60 | 2026-07-03 | ND-01 | TFS (part 3) — tests + docs | __tests__/tfs.test.ts, docs/help/tfs-destination.md | Vitest green; help article live. | Not Started
61 | 2026-07-04 | ND-02 | Holiday Tracker destination | integrations/holiday-tracker/* | API or DB write; mapping template; test against staging. | Not Started
62 | 2026-07-05 | WS-01 | Apify cloud actor wrapper (part 1) | integrations/scrape/apify/*, services/ApifyClient.ts | Configure target URL + selectors; trigger run; retrieve dataset. | Not Started
63 | 2026-07-06 | WS-01 | Apify (part 2) — scheduling + monitoring | services/ApifyClient.ts, workers/scrapeRunner.ts | Apify schedule integrated with BullMQ; failure alert dispatched. | Not Started
64 | 2026-07-07 | WS-02 | Playwright actor (part 1) — runtime | integrations/scrape/playwright/* | Recorded flow runs in worker; structured JSON returned. | Not Started
65 | 2026-07-08 | WS-02 | Playwright actor (part 2) — screenshot diff on failure | integrations/scrape/playwright/* | Failure captures screenshot; alert includes diff image. | Not Started
66 | 2026-07-09 | WS-02 | Playwright actor (part 3) — anti-detection basics + polish | integrations/scrape/playwright/* | Rotating UA; configurable delays; spider/bot icon in registry. | Not Started
Days Done |  |  | In Progress
Total Days | 66
% Complete

## 5. Phase 3 Day Plan
Phase 3 — Scale & Governance
Days 67 → 95. Multi-tenant + governance + Phase-3 destinations.
Day # | Calendar Date | Story ID | Goal of the Day | Files Touched | Test That Proves Done | Status
1 | 2026-07-10 | SG-01 | Client App Registration backend + token issuance | api/clients.routes.ts, db/schema.ts (client_apps) | External app registers; client_id + secret returned; stored hashed. | Not Started
2 | 2026-07-11 | SG-01 | Client App lifecycle (refresh + revoke + per-client dashboard) | components/admin/ClientApps.jsx, api/clients.routes.ts | Refresh + revoke endpoints; admin sees per-client volume + tier. | Not Started
3 | 2026-07-12 | SG-02 | Entity merge — backend impact analysis | services/EntityMergeService.ts, api/entities.routes.ts | POST /:id/merge dry-run returns affected adapters list. | Not Started
4 | 2026-07-13 | SG-02 | Entity merge — UI side-by-side diff | components/catalog/MergeModal.jsx | Designer selects 2 entities; diff shown; pick fields to keep. | Not Started
5 | 2026-07-14 | SG-02 | Entity merge — commit + post-merge re-test flag | services/EntityMergeService.ts (commit), workers/integrationRunner.ts | On commit, affected integrations flagged; banner on Registry cards. | Not Started
6 | 2026-07-15 | SG-03 | Entity evolution — add/rename field with cascade preview | services/EntityEvolutionService.ts, components/catalog/AddFieldModal.jsx | Designer adds field; sees downstream mapping impact before commit. | Not Started
7 | 2026-07-16 | SG-03 | Entity evolution — preview-before-commit + rollback | services/EntityEvolutionService.ts (rollback) | Mistakes can be reverted within 1 hour window. | Not Started
8 | 2026-07-17 | SG-04 | Self-healing service (part 1) — diagnose common failures | services/SelfHealingService.ts | Failure pattern catalog; LLM-driven root-cause classifier. | Not Started
9 | 2026-07-18 | SG-04 | Self-healing (part 2) — propose fix + dry-run | services/SelfHealingService.ts (propose) | Auto-suggested fixes shown to admin; dry-run validates before apply. | Not Started
10 | 2026-07-19 | SG-04 | Self-healing (part 3) — auto-apply opt-in + audit | services/SelfHealingService.ts (apply), middleware/audit.ts | Admin opts adapter into auto-apply; every fix logged. | Not Started
11 | 2026-07-20 | SG-04 | Self-healing (part 4) — UI banners + reporting | components/dashboard/HealingBanner.jsx, components/dashboard/HealingReport.jsx | Banner on dashboard; weekly self-healing report. | Not Started
12 | 2026-07-21 | SG-05 | Webhook support — outbound adapter | integrations/webhook/*, services/WebhookPushService.ts | Outbound webhook with HMAC sign; delivery retry policy. | Not Started
13 | 2026-07-22 | SG-05 | Webhook support — inbound handler + ingest | api/webhooks.routes.ts (inbound), services/WebhookIngestService.ts | Inbound webhook validates HMAC; pushes to integration as if API event. | Not Started
14 | 2026-07-23 | SG-06 | Bulk operations — multi-select + actions | components/registry/RegistryPage.jsx (selection), api/integrations.routes.ts (bulk) | Select multiple → Pause/Resume/Re-test actions; confirm modal. | Not Started
15 | 2026-07-24 | SG-06 | Bulk operations — batch re-test after entity change | services/BulkOpsService.ts | Triggered from entity merge/evolution flow; progress shown. | Not Started
16 | 2026-07-25 | SG-07 | Audit middleware writes — every state-changing route | middleware/audit.ts, all routes | Each POST/PATCH/DELETE writes audit row with diff + user + IP. | Not Started
17 | 2026-07-26 | SG-07 | Audit log UI timeline + filters | components/admin/AuditTimeline.jsx | Timeline view; filter by user, entity, action; export CSV. | Not Started
18 | 2026-07-27 | SG-08 | Resource-level RBAC — backend | db/schema.ts (user_overrides), middleware/withRole.ts | Per-adapter Designer access for an Operator on one connector only. | Not Started
19 | 2026-07-28 | SG-08 | Resource-level RBAC — admin UI | components/admin/PermissionOverrides.jsx | Admin grants/revokes resource-level permissions. | Not Started
20 | 2026-07-29 | SG-09 | AI Help Assistant (part 1) — chat backend | services/HelpAssistantService.ts, api/help.routes.ts | POST /api/help/ask; LLM with help library + screen state context. | Not Started
21 | 2026-07-30 | SG-09 | AI Help Assistant (part 2) — UI in HelpPanel | components/layout/HelpPanel.jsx (chat tab) | Chat tab in help panel; conversational; suggests next steps. | Not Started
22 | 2026-07-31 | SG-09 | AI Help Assistant (part 3) — context awareness | services/HelpAssistantService.ts (context loader) | Assistant sees current screen + recent actions; suggests context-aware next steps. | Not Started
23 | 2026-08-01 | SG-09 | AI Help Assistant (part 4) — guardrails + cost cap | services/HelpAssistantService.ts (rate limit + token cap) | Per-user daily token cap; rate limit; safety filter on output. | Not Started
24 | 2026-08-02 | SG-10 | Ahrefs destination connector | integrations/ahrefs/*, services/AhrefsPushService.ts | REST API + token; rank tracking entity templates; tests. | Not Started
25 | 2026-08-03 | SG-11 | Google Search Console destination | integrations/gsc/*, services/GSCPushService.ts | Service account / OAuth; performance + coverage entities. | Not Started
26 | 2026-08-04 | SG-11 | GSC — testing + docs | __tests__/gsc.test.ts, docs/help/gsc-destination.md | Vitest green; help article live. | Not Started
27 | 2026-08-05 | SG-12 | Google Adwords destination (part 1) — auth + dev token | integrations/google-ads/* | OAuth2 + developer token; refresh token storage. | Not Started
28 | 2026-08-06 | SG-12 | Google Adwords destination (part 2) — campaigns/ad-groups | integrations/google-ads/templates/* | Entity templates; create + update via Google Ads API. | Not Started
29 | 2026-08-07 | SG-12 | Google Adwords destination (part 3) — testing + go-live | __tests__/google-ads.test.ts | Sandbox account verified; help article live. | Not Started
Days Done |  |  | In Progress
Total Days | 29
% Complete

## 6. Phase 4 Day Plan
Phase 4 — Polish & Distribution
Days 96 → 112. Theming + PWA + onboarding + Docker + docs + final QA.
Day # | Calendar Date | Story ID | Goal of the Day | Files Touched | Test That Proves Done | Status
1 | 2026-08-08 | P4-01 | Theme engine (light/dark + custom logo upload) | contexts/ThemeContext.jsx, components/admin/BrandingTab.jsx | Toggle persists per user; logo upload validated + stored. | Not Started
2 | 2026-08-09 | P4-02 | Mobile PWA — manifest + service worker | public/manifest.json, src/serviceWorker.js | Lighthouse PWA score >90; installable on Android. | Not Started
3 | 2026-08-10 | P4-02 | Mobile PWA — responsive break-points | src/styles.css (media queries) | Dashboard + Monitor + Alerts usable on tablet (768px) and phone (375px). | Not Started
4 | 2026-08-11 | P4-02 | Mobile PWA — offline fallback for critical pages | src/serviceWorker.js (cache strategies) | Last-seen Health Dashboard renders offline. | Not Started
5 | 2026-08-12 | P4-03 | Onboarding wizard (part 1) — 5-step welcome | components/onboarding/OnboardingWizard.jsx | First-login users walk through 5 screens; skip + replay. | Not Started
6 | 2026-08-13 | P4-03 | Onboarding wizard (part 2) — sample data + sandbox | components/onboarding/SampleData.jsx | User can spin up demo Jira→SP integration in <2 minutes. | Not Started
7 | 2026-08-14 | P4-04 | Docker image build + compose | Dockerfile, docker-compose.prod.yml | Single image runs FE + BE; compose includes Postgres + Redis. | Not Started
8 | 2026-08-15 | P4-04 | One-command deploy script + .env.template | scripts/deploy.sh, .env.template | Fresh server: docker compose up reaches healthy state. | Not Started
9 | 2026-08-16 | P4-05 | Architecture guide + ADRs | docs/architecture.md, docs/adr/*.md | ADRs for auth, RBAC, sandboxing, AI mapping, encryption. | Not Started
10 | 2026-08-17 | P4-06 | User manual — Operator guide | docs/user-manual/operator.md (+ screenshots) | Step-by-step with screenshots; reviewed by 1 BA. | Not Started
11 | 2026-08-18 | P4-06 | User manual — Designer + Admin guides | docs/user-manual/{designer,admin}.md | All three guides published; cross-linked from Help panel. | Not Started
12 | 2026-08-19 | P4-07 | API reference (OpenAPI auto-gen) | scripts/generate-openapi.js, docs/api/* | OpenAPI YAML generated from routes; published as Redoc site. | Not Started
13 | 2026-08-20 | P4-08 | Handover package (zip everything) | scripts/handover-pack.sh | Single archive: BRD + plan + manuals + ADRs + runbook. | Not Started
14 | 2026-08-21 | P4-09 | Final QA — Playwright e2e suite (part 1) | e2e/*.spec.ts (Wizard, Mapping, Push) | 5 critical flows green in <10 min CI run. | Not Started
15 | 2026-08-22 | P4-09 | Final QA — Playwright e2e (part 2 — Admin + Alerts) | e2e/admin.spec.ts, e2e/alerts.spec.ts | User mgmt + alert flow tests green. | Not Started
16 | 2026-08-23 | P4-09 | Final QA — Playwright e2e (part 3 — multi-connector regression) | e2e/multi-connector.spec.ts | Dynamics, PostgreSQL, Excel, Keka, TARA, TFS, GSC sample paths green. | Not Started
17 | 2026-08-24 | P4-09 | Final go-live demo + retrospective | — | Demo to stakeholders; lessons-learned log captured. | Not Started
Days Done |  |  | In Progress
Total Days | 17
% Complete

## 7. Milestones
Milestones & Demos
Key checkpoint dates calibrated to the day plans. Update Status as each is reached.
# | Milestone | Phase | Day # | Calendar Date | Outcome / Demo Script | Status
1 | Auth + RBAC live | P2 | 5 | 2026-05-09 | Login screen works; protected routes enforce role; audit log captures auth events. | Not Started
2 | Frontend wired (Dashboard, Registry, Vault, Admin) | P2 | 11 | 2026-05-15 | End of Foundation week — no more mock data on these pages. | Not Started
3 | Connector Studio enabled | P2 | 20 | 2026-05-24 | Designer can publish a new REST connector end-to-end (Test → Publish → appears in Registry). | Not Started
4 | Master Catalog read-mode live | P2 | 24 | 2026-05-28 | CatalogPage shows real entities + field usage; cross-references work. | Not Started
5 | AI Auto-Map demo | P2 | 32 | 2026-06-05 | Wizard step 4 / Canvas: AI suggestions, NL transforms, sandbox transformations applied to a real push. | Not Started
6 | Trading Console + Health Dashboard live | P2 | 37 | 2026-06-10 | Real-time message stream visible; KPI tiles + charts populated; pause-and-inspect demo. | Not Started
7 | Alerts dispatching (in-app + email) | P2 | 42 | 2026-06-15 | Manufactured failure → email to Operator + Designer within 5 minutes. | Not Started
8 | Multi-source demo (PostgreSQL + Excel) | P2 | 50 | 2026-06-23 | Two new sources demoed; same wizard flow as Jira. | Not Started
9 | Dynamics + Keka + TARA online | P2 | 60 | 2026-07-03 | Three more sources live; coverage matrix updated. | Not Started
10 | TFS + Holiday Tracker destinations | P2 | 65 | 2026-07-08 | Two destinations beyond SharePoint live; Jira→TFS demo. | Not Started
11 | Web Scraping (Apify + Playwright) | P2 | 66 | 2026-07-09 | End of Phase 2. One Apify and one Playwright scraping connector running on a schedule. | Not Started
12 | Client App Registration + bulk ops | P3 | 72 | 2026-07-15 | External app registers, gets token, calls API; bulk pause demoed. | Not Started
13 | Entity merge + evolution | P3 | 78 | 2026-07-21 | Two overlapping entities merged with impact preview; field added with cascade. | Not Started
14 | Self-healing live | P3 | 84 | 2026-07-27 | Common failure auto-fixed in dry-run; admin opts adapter into auto-apply. | Not Started
15 | AI Help Assistant | P3 | 92 | 2026-08-04 | Conversational help with screen-state context; demo end-to-end. | Not Started
16 | Phase 3 destinations (Ahrefs + GSC + Adwords) | P3 | 95 | 2026-08-07 | End of Phase 3. All charter destinations on the board. | Not Started
17 | Theme engine + PWA | P4 | 99 | 2026-08-11 | Light/dark toggle; install on phone; offline Health Dashboard. | Not Started
18 | Onboarding wizard live | P4 | 101 | 2026-08-13 | First-login flow demoed; new user gets to a sample integration in <2 min. | Not Started
19 | Docker one-command deploy | P4 | 103 | 2026-08-15 | Fresh VM → docker compose up → app reachable + healthy. | Not Started
20 | Handover package + docs complete | P4 | 108 | 2026-08-20 | Architecture guide + 3 user manuals + API ref + handover zip. | Not Started
21 | Production handover demo | P4 | 112 | 2026-08-24 | Final stakeholder demo; project plan signed off. | Not Started

## 8. Gantt
Gantt — Epic Timeline
Total span: Day 1 → Day 112 (2026-05-05 → 2026-08-24). Bars filled in NAVY; phase bands in DEEP/ORANGE.
Epic | Phase | Start Day | End Day | Duration | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112
Foundation: Auth + Wiring | P2 | 1 | 11 | 11
Connector Studio | P2 | 12 | 20 | 9
Master Entity Catalog (read) | P2 | 21 | 24 | 4
Mapping Engine + AI Auto-Map | P2 | 25 | 32 | 8
Monitoring (Console + Dashboard) | P2 | 33 | 37 | 5
Alerts System | P2 | 38 | 42 | 5
Help System | P2 | 43 | 47 | 5
New Sources (PG/Excel/D365/Keka/TARA) | P2 | 48 | 60 | 13
New Destinations (TFS + Holiday) | P2 | 61 | 65 | 5
Web Scraping (Apify + Playwright) | P2 | 66 | 66 | 1
Client Apps + Lifecycle | P3 | 67 | 68 | 2
Entity Merge + Evolution | P3 | 69 | 73 | 5
Self-Healing | P3 | 74 | 77 | 4
Webhook Support + Bulk Ops | P3 | 78 | 81 | 4
Audit + Resource RBAC | P3 | 82 | 85 | 4
AI Help Assistant | P3 | 86 | 89 | 4
Phase 3 Destinations (Ahrefs/GSC/Adwords) | P3 | 90 | 95 | 6
Theme + PWA | P4 | 96 | 99 | 4
Onboarding + Packaging | P4 | 100 | 103 | 4
Documentation | P4 | 104 | 108 | 5
Final QA + Demo | P4 | 109 | 112 | 4
Legend
Phase 2
Phase 3
Phase 4

## 9. Risks
Risk Register
Charter risks + code-level risks discovered during walkthrough. Update Status weekly.
# | Risk | Likelihood | Impact | Mitigation | Owner | Status
1 | External API access not obtainable for some destinations | Medium | High | Three-tier fallback: browser passthrough → Apify cloud → Playwright self-hosted. Scraping connectors flagged with bot icon and monitored. | Designer | Not Started
2 | Web scraping connectors break on UI changes | High | Medium | Screenshot-diff alerting on scrape failures; designer notified immediately with diff image. | Designer | Not Started
3 | Scope creep expands beyond planned phases | High | High | Lock scope per phase; change-request process; MVP-first discipline; milestones reviewed weekly. | Product Owner | Not Started
4 | AI Auto-Map produces poor suggestions | Medium | Medium | Always require human confirmation; log decisions for tuning; graceful fallback to manual mapping. Target ≥70% accuracy. | Designer | Not Started
5 | Non-technical users find mapping too complex | Medium | High | Extensive UX testing; progressive disclosure; task escalation to Designer; first-time walkthroughs. | PM | Not Started
6 | Credential vault security vulnerability | Low | Critical | AES-256-GCM; security review before any external exposure; no raw credential display anywhere; reveal events audited. | Admin | Not Started
7 | 10 of 11 frontend pages on mock data — silent regressions when wired | High | Medium | End-to-end Playwright test added at the time of wiring each page (test-first). | Developer | Not Started
8 | No auth enforcement today — accidental public exposure if deployed | Medium | Critical | Lock to localhost / VPN until F-01/F-02/F-03 ship; no production deploy until RBAC live. | Admin | Not Started
9 | Single-developer bus factor + vibe-coding velocity dependence | Medium | High | Strong PRODUCT_STATUS.md + BRD + day-level plan keep the project transferable; CLAUDE.md captures session conventions. | PM | Not Started
10 | AI mapping cost overruns (Anthropic API) | Medium | Medium | Daily cost cap per environment; cache layer; configurable rate limit; monitor in dashboard. | Developer | Not Started
11 | JS sandbox escape risk in transformations | Low | Critical | QuickJS in worker thread; strict CPU/memory limits; no host fs/network access from sandbox; security review. | Developer | Not Started
12 | Long-running queue jobs starve other work | Medium | Medium | Per-queue concurrency limits; separate queue for scraping; BullMQ priority levels for critical alerts. | Developer | Not Started
13 | Schema migration breaks running adapters | Medium | High | Drizzle migrations versioned; pre-deploy dry-run on shadow DB; rollback plan documented per migration. | Developer | Not Started
14 | Email transport delivery issues (alerts ignored) | Low | High | Health probe sends test email weekly; SMTP fallback to alternate provider; in-app bell as backup channel. | Admin | Not Started
15 | Tech-stack lock-in to React 19 / Express 5 / Drizzle | Low | Low | Documented in BRD §11.2. Acceptable trade-off for velocity; modular service layer minimises lock-in cost. | Architect | Not Started

## 10. Open Decisions
Open Decisions
Charter open decisions + new code-level decisions discovered during BRD walkthrough.
# | Decision | Options | Recommendation | Decide By (Day) | Decide By (Date) | Status
1 | AI provider for mapping | OpenAI / Claude API / Local model | Claude API — already used; cost-effective at this volume. | 1 | 2026-05-05 | Not Started
2 | Charting library | Recharts / Chart.js / D3 | Recharts — declarative, works cleanly with React 19. | 1 | 2026-05-05 | Not Started
3 | Web scraping provider | Apify (cloud) / Playwright (self) / Both | Both — Apify for quick setups, Playwright for complex flows. | 7 | 2026-05-11 | Not Started
4 | Auth strategy | Local (JWT) / SSO (Azure AD) / Both | Local JWT first; pluggable adapter for SSO in Phase 3. | 1 | 2026-05-05 | Not Started
5 | Help content authoring | Markdown in repo / CMS / Wiki | Markdown in repo; index built at build time (lunr.js). | 28 | 2026-06-01 | Not Started
6 | Email transport | SMTP / SES / SendGrid | Start SMTP via env; swap for SES in Phase 4 if volume warrants. | 38 | 2026-06-11 | Not Started
7 | JS sandbox for transformations | vm2 / QuickJS / WASM | QuickJS — modern, sandboxed, low overhead, in worker thread. | 25 | 2026-05-29 | Not Started
8 | Hosting model | Local server / Docker / Cloud (Azure/AWS) | Start local + Docker for portability; cloud as Phase 4 outcome. | 96 | 2026-08-08 | Not Started
9 | First non-Jira / non-SharePoint connector pair to demo | PostgreSQL → TFS / Excel → Holiday Tracker / Dynamics → SharePoint | PostgreSQL → TFS — both new, exercises Studio + new dest path. | 11 | 2026-05-15 | Not Started
10 | Multi-tenancy go-live | Phase 2 (with auth) / Phase 3 (with client apps) | Phase 3 — keep Phase 2 single-tenant to ship fast; org isolation lands with client apps. | 66 | 2026-07-09 | Not Started
11 | AI Help Assistant scope | Library-only / + Screen state / + Action history | Full context (library + state + history) at Phase 3 launch. | 86 | 2026-07-29 | Not Started
12 | Mobile PWA depth | Read-only / Read+limited write / Full parity | Read-only at launch; expand based on actual mobile usage. | 96 | 2026-08-08 | Not Started